“FOXY ROXY and the HIDEBEHIND” BUDGET:

PRE-PRODUCTION:

	Expense:
	Cost:

	Screenplay
	$0/self

	Casting:
	$0/self

	Producer (s)
	$500

	Location
	$0 donated

	
	

	
	

	
	



PRODUCTION:

	Expense:
	Cost:	

	Cast: Roxy, Tony, Hidebehind
	$250/day: $750, $250, $500

	Costume and Makeup
	$120

	Lodging/travel
	$300 - $500

	1st AD
	One of the Producers and the AD are the same person.

	Director
	$500

	Craft
	$120/day: $360 total

	PA’s
	$150/day: $450 total

	Total
	$2,480

	DP
	N/A (Found Footage/actress)

	Sound Mixer
	N/A




POST-PRODUCTION:

	Expense:
	Cost:

	Editing
	$0/self

	Sound Editing/scoring
	$500

	Coloring:
	$0/self

	
	

	
	

	
	

	
	



TOTAL: $4,230	


TIMELINE:
Planning on a three-day shoot in either May of 2025 or October 2025. The reason for the two dates is the location is on a private road that is closed during the winter because of snow. If enough of the snow as melted by the time of the May shoot AND my lead actress can do those dates, then it is May, otherwise we most likely have to reschedule for fall.

The Shoot will be on a Thursday, through that Saturday. May 15-17, 2025 or October 16-18, 2025.
The plan is to shoot everything in the first two days, third for reshoots. If the reshoots are not needed then everyone will be paid the full amount, regardless. 

Day 1: the final scene (halfway through page 10 through page 12) in the early morning. Pages 1- 6 and the montage on the beginning of page 7, from late morning until late afternoon (just before sunset)

Day 2: Pages 6-7, sunset til 1 am.
Morning of day 2 will be used reviewing the footage from Day 1 to see if any reshoots are needed.

Day 3: Re-shoot as needed.


REFERENCES:
Kaily Jacobs: kaily.luvstosing@gmail.com   Phone: 801-414-0027
Dale Nielson: 801-403-4676
Jon Cooper: thescreenwritingdoctor@gmail.com
