## Summary
Check, Cheap, All In, or Fold — Four Budget Options
Detailed short-film planning model ¦ USD ¦ 2026 labor references ¦ All five speaking performers and all visible poker props are paid
Scenario | Estimated Total | Shoot Days | Prep Weeks | Post Weeks | Budget / Finished Min. | Paid Props | Performer Framework | Production Approach
Micro Budget | 17908.9963 | 2 | 1 | 2 | 1193.9331 | 1050 | SAG-AFTRA Micro-Budget route if eligible; compensation negotiated and paid | Two tightly planned shoot days; local cast and crew; an existing room redressed; compact camera/G&E package; paid poker props; streamlined post and festival deliverables.
Ultra-Low Budget | 82222.35 | 2 | 2 | 4 | 5481.49 | 3090 | SAG-AFTRA Ultra Low Budget Project Agreement (UPA) planning case | Professional local crew, two shoot days plus rehearsal, controlled private-room location, stronger art/lighting/sound, continuity duplicates, complete sound/color, captions, DCP, and E&O.
Low Budget | 246442.7852 | 3 | 3 | 6 | 16429.519 | 6910 | SAG-AFTRA UPA minimums with negotiated overscale performer placeholders | Three-day coverage plan for a dialogue-heavy ensemble; experienced department heads; designed poker room; cinema package, dolly and video village; enhanced post, publicity, and delivery.
Production Company | 592679.8458 | 4 | 5 | 8 | 39511.9897 | 14450 | SAG-AFTRA Moderate Low Budget (MPA) / DGA Level 1a planning framework | Production-company execution with overscale cast, staffed departments, stage/control days, custom poker-room finish, premium equipment, full editorial/sound/color pipeline, EPK, legal, and distribution-ready masters.
Cost by department
Department | Micro Budget | Ultra-Low Budget | Low Budget | Production Company
Development & Above-the-Line | 1300 | 7900 | 23500 | 60000
Cast | 3559.375 | 6815 | 13032 | 35268.75
Production Management | 1880 | 9007.5 | 22849 | 49276
Camera | 1346 | 6560 | 17845.5 | 39120
Grip & Electric | 1570 | 5535 | 15996 | 33652
Production Sound | 673 | 2915 | 7162.5 | 14532
Art Department & Paid Props | 1692 | 10245 | 30331.5 | 70138
Wardrobe / Hair / Makeup | 767 | 3032.5 | 9704.5 | 20544
Locations | 600 | 5112.5 | 14913 | 42680
Transportation & Meals | 970 | 3072 | 8950 | 21420
Post-Production | 2230 | 12962.5 | 44028 | 93884
Insurance / Legal / Admin / Marketing | 800 | 5150 | 15300 | 37200
How to use this workbook
Blue/yellow cells are editable planning inputs. Green formulas link assumptions, cast, props, budget tabs, and this summary. Change quantities, rates, burdens, contingency, overhead, or schedule inputs to recalculate the model.
Micro is designed to remain within SAG-AFTRA’s $20,000 Micro-Budget cap. Ultra-Low and Low are both below the UPA’s $300,000 maximum. The Production Company case is designed below the MPA’s $700,000 maximum. Eligibility still depends on the final release plan and union approval.
The screenplay’s true cost driver is not locations or action—it is performance coverage and poker continuity. Protect rehearsal time, script supervision, prop-master preparation, and systematic inserts before adding production value elsewhere.
These are gross 2026 planning estimates, not bids. Obtain location-specific payroll, guild, insurance, equipment, post, legal, and prop quotes before financing or greenlight.

## Assumptions
Check, Cheap, All In, or Fold — Four-Tier Budget Assumptions
Short screenplay ¦ USD ¦ 2026 planning estimate ¦ Edit blue/yellow inputs; green text links between sheets
Section | Driver | Units | Micro Budget | Ultra-Low Budget | Low Budget | Production Company | Notes / source
Schedule | Principal photography | days | 2 | 2 | 3 | 4 | Dialogue and poker-hand continuity drive the schedule
Schedule | Prep | weeks | 1 | 2 | 3 | 5 | Includes blocking, poker rehearsal, art, camera, and location prep
Schedule | Post-production | weeks | 2 | 4 | 6 | 8 | Calendar duration; not every department works full time
Format | Estimated finished runtime | minutes | 15 | 15 | 15 | 15 | Planning midpoint; screenplay reads as an approximately 14–16 minute short
Labor | Illustrative performer framework | text | SAG-AFTRA Micro-Budget route if eligible; compensation negotiated and paid | SAG-AFTRA Ultra Low Budget Project Agreement (UPA) planning case | SAG-AFTRA UPA minimums with negotiated overscale performer placeholders | SAG-AFTRA Moderate Low Budget (MPA) / DGA Level 1a planning framework | Final contract choice depends on budget, release plan, signatory status, and SAG-AFTRA approval
Labor | Principal performer daily reference | $/day | 225 | 257 | 257 | 449 | Micro is a paid negotiated placeholder; 2026 UPA $257/day; 2026 MPA $449/day
Labor | Cast pension & health | % of principal payroll | 0% | 22% | 22% | 22% | Planning rate after 2026-09-06; confirm with assigned SAG-AFTRA representative
Labor | Cast payroll taxes / workers comp | % of principal payroll | 12% | 12% | 12% | 12% | Editable employer-side planning load
Labor | Crew payroll burden | % of employee wages | 12% | 15% | 19% | 24% | Payroll taxes, workers compensation, and tier-dependent benefits
Labor | Entertainment payroll service | % of principal payroll | 3% | 3% | 3% | 3.5% | Applied separately to principal performer gross
Risk | Contingency | % of pre-contingency subtotal | 3% | 5% | 7% | 8% | Covers modest schedule, equipment, location, continuity, and delivery variance
Company | Production-company overhead | % of direct subtotal | 0% | 0% | 3% | 6% | Included at the low and production-company tiers
Production | Primary base | text | Local U.S. market | Local U.S. market | Regional production center | Major U.S. production center | Local hires; no travel or lodging assumed
Crew | Guild / union posture | text | Nonunion or SAG Micro | SAG UPA; crew terms quoted locally | SAG UPA; union crew if applicable | SAG MPA; DGA/IATSE/Teamsters as applicable | Obtain guild and payroll quotes before greenlight
Incentives | Tax credits, rebates, grants | netted? | No | No | No | No | Gross budgets; no incentive proceeds reduce displayed totals
Currency | Budget currency | currency | USD | USD | USD | USD | Vendor quotes, taxes, and local wage rules can materially change costs
Color legend
Blue text / yellow fill | Editable input | [5 empty] | Changeable planning assumption
Green text | Internal workbook link | [5 empty] | Formula references another worksheet
Black text | Calculation / label | [5 empty] | Formula or descriptive content

## Script Breakdown
Screenplay Production Breakdown
Check, Cheap, All In, or Fold ¦ Source: Pasted text(20260816-042352).txt ¦ Breakdown dated 2026-08-15
Core scope
Driver | Screenplay finding | Budget impact | Micro | Ultra-Low | Low | Production Co | Scheduling / production note
Format / runtime | Short screenplay; approximately 2,651 words | Approx. 14–16 finished minutes | 15 min plan | 15 min plan | 15 min plan | 15 min plan | Final runtime depends on performance pace and montage
Locations | One interior private poker room | Major containment advantage | Existing room | Existing private room | Designed room | Stage or premium location | Prep/strike access is budgeted separately from shoot days
Speaking cast | Five: Chip, Kimber, Kennedy, Miles, Holden | All appear throughout | Paid | Paid | Paid | Paid overscale | No background performers are required by the text
Story time | One night | Single wardrobe continuity | One look each | One look each | Designed looks | Designed looks + backups | Fittings and wardrobe allowance included
Poker action | Many specific deals, folds, board cards, bets, chip stacks, and reveals | Continuity-intensive | Hand charts | Prop master | Prop master + script supervisor | Dedicated card/chip continuity | Photograph every setup; prepare cards and chip stacks in advance
Montage | Series of quick hands | Additional inserts and reset time | Compressed | Planned inserts | Dedicated insert block | Dedicated insert unit / motion control as useful | Schedule inserts by hand and chip configuration
Special photography | Slow-motion final image | High-frame-rate capture / lighting | Camera capability | Camera capability | Dedicated setup | Premium high-speed setup | No meaningful VFX required beyond cleanup and polish
Stunts / safety | No scripted hazardous stunt, weapon, intimacy, animal, vehicle, or minor work | Low risk | None | None | None | None | Normal set safety, medic, and insurance still apply
Sound | Five-person overlapping dialogue in one room | Lav coverage and room control | Mixer + compact kit | Mixer + boom | Mixer + boom + timecode | Full production sound team | Quiet HVAC and room tone are important
Set look | Green-felt table under a cone of warm light; surrounding darkness | Lighting and practical control | Redress | Art-directed redress | Designed environment | Custom finish | The look is simple but must feel intentional rather than empty
Cast breakdown
Character | Age / description | Dialogue load | Poker/business | Wardrobe | Shoot continuity | Risk | Budget note
CHIP | 40; self-assured instructor/dealer | Lead / very high | Expert card handling and teaching | Contemporary smart casual | Every setup | Low | Budget rehearsal for dealing, blocking, and dialogue pace
KENNEDY | 20; quietly intelligent, unreadable | Supporting lead; late payoff | Controlled play, final reveals | Contemporary understated | Every setup | Low | Performance and hand-reveal coverage are central to ending
KIMBER | 24; quick-witted | Major supporting | Cruise motivation; active betting | Contemporary polished | Every setup | Low | Position to Chip’s left must remain consistent
MILES | 22; intensely analytical | Major supporting | Analysis beats; diamond-flush reveal | Contemporary neat | Every setup | Low | Specific losing hand and chip action require reset photos
HOLDEN | 23; cocky | Major supporting | Aggressive betting; comic reactions | Contemporary confident | Every setup | Low | Position to Chip’s right must remain consistent
Production priorities
1 | Pre-block the seating and eyelines | Kimber, Kennedy, Miles, and Holden must remain in the scripted order around Chip |  |  |  |  | Avoid coverage that reverses geography
2 | Build a hand-by-hand continuity bible | Record hole cards, community cards, puck position, chip stacks, pot size, and folds for every beat |  |  |  |  | The prop and script departments share this responsibility
3 | Protect performance time | The script is dialogue-heavy; schedule table reads and do not assume one-day coverage |  |  |  |  | Micro still uses two shoot days
4 | Control reflections and card readability | Glossy chips/cards, the overhead practical, and dark surroundings can create glare or unreadable values |  |  |  |  | Test the actual hero deck, chips, and felt with the lens package
5 | Shoot inserts systematically | Group card, chip, hand, dealer-button, and slow-motion inserts after master coverage |  |  |  |  | Reduces reset and continuity errors

## Cast & Schedule
Paid Cast Plan & Schedule
All five speaking performers are paid; workdays include rehearsals/table work where shown ¦ Rates are editable planning assumptions
Role | Function / continuity | Wardrobe | Micro days | Micro rate | Micro gross | Ultra days | Ultra rate | Ultra gross | Low days | Low rate | Low gross | Prod. days | Prod. rate | Prod. gross
CHIP | Lead; dealer/instructor; expert shuffle and deal | 1 look | 2.5 | 225 | 562.5 | 3 | 300 | 900 | 4 | 500 | 2000 | 5.5 | 1000 | 5500
KENNEDY | Supporting lead; restrained performance; final winning reveals | 1 look | 2.5 | 225 | 562.5 | 3 | 300 | 900 | 4 | 450 | 1800 | 5.5 | 900 | 4950
KIMBER | Major supporting; seated left of Chip | 1 look | 2.5 | 225 | 562.5 | 3 | 300 | 900 | 4 | 400 | 1600 | 5.5 | 800 | 4400
MILES | Major supporting; analytical beats; diamond-flush reveal | 1 look | 2.5 | 225 | 562.5 | 3 | 300 | 900 | 4 | 400 | 1600 | 5.5 | 800 | 4400
HOLDEN | Major supporting; seated right of Chip; aggressive betting | 1 look | 2.5 | 225 | 562.5 | 3 | 300 | 900 | 4 | 400 | 1600 | 5.5 | 800 | 4400
GROSS PRINCIPAL PAYROLL |  |  |  |  | 2812.5 |  |  | 4500 |  |  | 8600 |  |  | 23650
Schedule logic
Micro | Half-day table read/card rehearsal + 2 shoot days
Ultra-Low | 1 paid rehearsal/table day + 2 shoot days
Low | 1 paid rehearsal/blocking day + 3 shoot days
Production Co | 1 table read + half-day cards/camera rehearsal + 4 shoot days
All tiers | No unpaid cast, background, minors, stunt performers, or stand-ins are assumed

## Props & Art
Paid Props & Set-Dressing Ledger
Every visible poker asset is purchased, fabricated, or rented—nothing is treated as free ¦ Paid asset totals feed all four budgets
Category | Item | Script / continuity purpose | Acquisition | Quantity / planning note | Micro Budget | Ultra-Low Budget | Low Budget | Production Company
Hero set piece | Green-felt round poker table | Primary playing surface; camera-safe finish and rail | Rent / buy / custom by tier | 1 hero table | 250 | 750 | 1500 | 3000
Furniture | Padded poker chairs | Chip plus four mentees; consistent seating geography | Rent / buy | 5 matching or coordinated chairs | 100 | 300 | 750 | 1500
Hero props | Tournament poker chip sets | Stacks, blinds, bets, five-stack raise, and massive final pot | Buy / premium rental | Multiple colors/denominations plus overage | 175 | 450 | 900 | 1800
Hero props | Playing-card decks | Pre-set hole cards, board cards, folds, and reveals | Buy | Continuity duplicates; camera-tested backs/faces | 45 | 100 | 180 | 300
Hero props | Dealer button — the “puck” | Button-position dialogue and Kimber’s question | Buy | Hero plus spares | 15 | 40 | 80 | 150
Poker support | Chip racks and trays | Organize resets and protect chip-stack continuity | Buy | Enough for prebuilt hands and strike | 35 | 75 | 150 | 300
Surface support | Replacement felt / felt topper | Repairs, inserts, and clean green surface | Buy / fabricate | Color-matched spare material | 60 | 150 | 350 | 700
Practical lighting | Cone pendant lamp, bulbs, dimmer, cabling | Warm pool of light above the table | Rent / buy | Hero practical plus spare bulbs | 75 | 250 | 600 | 1200
Poker support | Cut cards, card guards, markers, small accessories | Smooth dealing and controlled resets | Buy | Camera-safe, nonbranded where possible | 25 | 50 | 100 | 200
Continuity | Labels, bags, hand charts, photo-board consumables | Track hole cards, board, puck, stacks, and pot by setup | Buy | Department continuity kit | 35 | 100 | 250 | 500
Storage | Lockable prop cases and transport bins | Secure hero chips/cards and prebuilt hands | Rent / buy | Tier-scaled | 25 | 75 | 200 | 500
Set dressing | Wall décor, side tables, practical accents | Create a believable private poker room beyond the pool of light | Rent / buy | Minimal to premium by tier | 100 | 400 | 1000 | 2500
Reserve | Continuity duplicates, damage, loss, and repairs | Replace marked cards, damaged chips/felt, or failed practicals | Reserve | Not assumed recoverable | 60 | 200 | 500 | 1000
Procurement | Prop-master petty cash, tax, and shipping | Last-mile sourcing and replacements | Allowance | Receipted purchases | 50 | 150 | 350 | 800
PAID PROP / SET-DRESSING TOTAL |  |  |  |  | 1050 | 3090 | 6910 | 14450
Continuity warning
The screenplay specifies numerous exact hands and board cards. Build a hand-by-hand continuity bible before photography; photograph the table after every approved setup and pre-bag each hero deck/stack configuration.
Avoid trademarked casino branding unless cleared. Verify chip colors, card indexes, and suit symbols read correctly on the selected camera and under the warm practical.

## Micro Budget
Check, Cheap, All In, or Fold — Micro Budget
Two tightly planned shoot days; local cast and crew; an existing room redressed; compact camera/G&E package; paid poker props; streamlined post and festival deliverables. ¦ USD ¦ Gross budget before incentives
Scenario | Grand Total | Shoot Days | Prep Weeks | Post Weeks | Paid Props | Gross Cast | Performer Framework | Planning Note
Micro Budget | 17908.9963 | 2 | 1 | 2 | 1050 | 2812.5 | SAG-AFTRA Micro-Budget route if eligible; compensation negotiated and paid | Two tightly planned shoot days; local cast and crew; an existing room redressed; compact camera/G&E package; paid poker props; streamlined post and festival deliverables.
Labor assumptions are planning inputs, not payroll quotations. Confirm the final SAG-AFTRA agreement, state/local wage law, overtime, meal penalties, workers compensation, and any IATSE/Teamsters/DGA obligations before hiring.
No tax credit, grant, rebate, sponsorship, product placement, donated labor, or in-kind equipment reduces this gross budget. Refundable deposits and union security deposits are cash-flow needs but are not treated as final costs unless retained.
Account | Category | Line Item | Basis | Qty | Rate / Linked Base | Fringe / Load | Line Total | Notes
0100 — Development & Above-the-Line
0101 | Development & Above-the-Line | Screenplay license / writer fee | flat | 1 | 200 | 0% | 200 | Paid rights/fee placeholder; replace with negotiated writer/producer deal
0102 | Development & Above-the-Line | Rewrite / production polish | flat | 0 | 0 | 0% | 0 | Final continuity and production draft
0103 | Development & Above-the-Line | Producer fee | flat | 1 | 300 | 0% | 300 | Excludes production-company overhead below
0104 | Development & Above-the-Line | Director fee | flat | 1 | 500 | 0% | 500 | DGA Level 1a compensation is negotiable when applicable
0105 | Development & Above-the-Line | Casting | flat | 1 | 100 | 0% | 100 | Five speaking roles; no background casting
0106 | Development & Above-the-Line | Poker consultant / hand-continuity design | flat | 1 | 100 | 0% | 100 | Verify gameplay, prebuild hands, coach dealing and chip action
0107 | Development & Above-the-Line | Business affairs / chain-of-title prep | flat | 1 | 100 | 0% | 100 | Rights, releases, guild setup, and entity records
DEVELOPMENT & ABOVE-THE-LINE SUBTOTAL | [6 empty] | 1300 | Account group 0100
0200 — Cast
0201 | Cast | Principal performers — five paid speaking roles | linked cast gross | 1 | 2812.5 | 0% | 2812.5 | Pulled from Cast & Schedule
0202 | Cast | SAG-AFTRA pension & health | % principal gross | 1 | 2812.5 | 0% | 0 | Applied to gross principal payroll; Micro left at 0% pending agreement choice
0203 | Cast | Employer payroll taxes / workers comp | % principal gross | 1 | 2812.5 | 12% | 337.5 | Editable planning load
0204 | Cast | Entertainment payroll service | % principal gross | 1 | 2812.5 | 3% | 84.375 | UPA requires entertainment payroll processing
0205 | Cast | Fittings / wardrobe allowance | flat | 1 | 125 | 0% | 125 | Five contemporary looks
0206 | Cast | Local mileage, parking, and meal incidentals | flat | 1 | 200 | 0% | 200 | No airfare or lodging assumed
CAST SUBTOTAL | [6 empty] | 3559.375 | Account group 0200
0300 — Production Management
0301 | Production Management | Line producer / UPM | workdays | 0 | 0 | 12% | 0 | Prep, production, wrap
0302 | Production Management | 1st assistant director | shoot days | 2 | 200 | 12% | 448 | Set operations and timing
0303 | Production Management | 2nd assistant director | shoot days | 0 | 0 | 12% | 0 | Cast flow, paperwork, and calls
0304 | Production Management | Production coordinator | workdays | 2 | 100 | 12% | 224 | Call sheets, vendors, releases, wrap
0305 | Production Management | Script supervisor | shoot days | 2 | 150 | 12% | 336 | Dialogue, eyeline, card, and chip continuity
0306 | Production Management | Production assistants | person-days | 4 | 100 | 12% | 448 | Set, lockup, runs, and strike
0307 | Production Management | Set medic / first aid | shoot days | 2 | 100 | 12% | 224 | Normal set safety coverage
0308 | Production Management | Production office / phones / printing | allowance | 1 | 100 | 0% | 100 | Digital paperwork plus essential hard copy
0309 | Production Management | Overtime / meal-penalty reserve | allowance | 1 | 100 | 0% | 100 | Separate from general contingency
PRODUCTION MANAGEMENT SUBTOTAL | [6 empty] | 1880 | Account group 0300
0400 — Camera
0401 | Camera | Director of photography | shoot days | 2 | 250 | 12% | 560 | DP operates at Micro/Ultra tiers
0402 | Camera | Camera operator | shoot days | 0 | 0 | 12% | 0 | Dedicated operator at higher tiers
0403 | Camera | 1st assistant camera | shoot days | 2 | 150 | 12% | 336 | Focus, lens changes, camera build
0404 | Camera | 2nd AC / loader | shoot days | 0 | 0 | 12% | 0 | Slates, media, reports
0405 | Camera | DIT / data wrangler | shoot days | 0 | 0 | 12% | 0 | Verified dual backups and look management
0406 | Camera | Camera and lens package | shoot days | 2 | 125 | 0% | 250 | Camera, lenses, support, filters
0407 | Camera | Media and production backup drives | allowance | 1 | 100 | 0% | 100 | At least two verified copies
0408 | Camera | Video village / wireless monitoring | package | 0 | 0 | 0% | 0 | Director, script, and client monitoring
0409 | Camera | Dolly / slider / gimbal | package | 1 | 50 | 0% | 50 | Slow push-ins and table movement
0410 | Camera | Camera expendables | allowance | 1 | 50 | 0% | 50 | Tape, wipes, batteries, adapters
CAMERA SUBTOTAL | [6 empty] | 1346 | Account group 0400
0500 — Grip & Electric
0501 | Grip & Electric | Gaffer | shoot days | 2 | 200 | 12% | 448 | Warm table pool and dark surround
0502 | Grip & Electric | Key grip | shoot days | 2 | 175 | 12% | 392 | Rigging, shaping, camera movement
0503 | Grip & Electric | Grip / electric swings | person-days | 2 | 125 | 12% | 280 | Tier-scaled crew
0504 | Grip & Electric | G&E package | shoot days | 2 | 150 | 0% | 300 | LEDs, stands, flags, rigging, distro
0505 | Grip & Electric | Power and distribution | allowance | 1 | 50 | 0% | 50 | Location-safe power plan
0506 | Grip & Electric | Practical lamp control / dimmers | allowance | 1 | 50 | 0% | 50 | Flicker-free bulbs and dimming
0507 | Grip & Electric | G&E expendables | allowance | 1 | 50 | 0% | 50 | Gel, tape, blackwrap, hardware
GRIP & ELECTRIC SUBTOTAL | [6 empty] | 1570 | Account group 0500
0600 — Production Sound
0601 | Production Sound | Production sound mixer | shoot days | 2 | 200 | 12% | 448 | Five-character dialogue
0602 | Production Sound | Boom operator | shoot days | 0 | 0 | 12% | 0 | Mixer booms in Micro case
0603 | Production Sound | Recorder / mixer / wireless package | shoot days | 2 | 75 | 0% | 150 | Five lavs, boom, timecode by tier
0604 | Production Sound | Additional lav / timecode / IFB | allowance | 1 | 50 | 0% | 50 | Tier-scaled coverage
0605 | Production Sound | Sound expendables | allowance | 1 | 25 | 0% | 25 | Batteries, mounts, tape, windscreens
PRODUCTION SOUND SUBTOTAL | [6 empty] | 673 | Account group 0600
0700 — Art Department & Paid Props
0701 | Art Department & Paid Props | Production designer | workdays | 0 | 0 | 12% | 0 | Concept, palette, location transformation
0702 | Art Department & Paid Props | Art director / set decorator | workdays | 0 | 0 | 12% | 0 | Sourcing, installation, returns
0703 | Art Department & Paid Props | Prop master / card continuity | workdays | 2 | 175 | 12% | 392 | Prebuild every hand and chip state
0704 | Art Department & Paid Props | Art / props production assistant | person-days | 0 | 0 | 12% | 0 | Prep, resets, strike
0705 | Art Department & Paid Props | Private poker-room build and dressing | allowance | 1 | 200 | 0% | 200 | Wall treatment, blackout, floor protection, install/strike
0706 | Art Department & Paid Props | Paid poker props and set dressing | linked prop total | 1 | 1050 | 0% | 1050 | Pulled from Props & Art
0707 | Art Department & Paid Props | Art transport, returns, and storage | allowance | 1 | 50 | 0% | 50 | Cargo, consumables, return fees
ART DEPARTMENT & PAID PROPS SUBTOTAL | [6 empty] | 1692 | Account group 0700
0800 — Wardrobe / Hair / Makeup
0801 | Wardrobe / Hair / Makeup | Costume designer / stylist | workdays | 0 | 0 | 12% | 0 | Five contemporary looks
0802 | Wardrobe / Hair / Makeup | Wardrobe purchases / rentals | allowance | 1 | 250 | 0% | 250 | Character-specific pieces and backups
0803 | Wardrobe / Hair / Makeup | Alterations, laundry, and returns | allowance | 1 | 50 | 0% | 50 | Prep and wrap
0804 | Wardrobe / Hair / Makeup | Hair and makeup key | shoot days | 2 | 175 | 12% | 392 | Camera-ready continuity
0805 | Wardrobe / Hair / Makeup | Hair / makeup assistant | shoot days | 0 | 0 | 12% | 0 | Higher-tier support
0806 | Wardrobe / Hair / Makeup | Wardrobe / HMU kits and expendables | allowance | 1 | 75 | 0% | 75 | Sanitary disposables and repair supplies
WARDROBE / HAIR / MAKEUP SUBTOTAL | [6 empty] | 767 | Account group 0800
0900 — Locations
0901 | Locations | Private poker room / stage | access days | 2 | 150 | 0% | 300 | Shoot plus prep/strike access by tier
0902 | Locations | Location manager / scout | workdays | 0 | 0 | 12% | 0 | Scout, contract, neighbors, logistics
0903 | Locations | Permit / film office / site representative | allowance | 1 | 100 | 0% | 100 | Jurisdiction and venue dependent
0904 | Locations | Cleaning, utilities, floor protection, damage reserve | allowance | 1 | 100 | 0% | 100 | Not the refundable security deposit itself
0905 | Locations | Parking, holding, restroom, and security | allowance | 1 | 100 | 0% | 100 | Crew/cast base support
LOCATIONS SUBTOTAL | [6 empty] | 600 | Account group 0900
1000 — Transportation & Meals
1001 | Transportation & Meals | Production van / cargo vehicle | rental days | 0 | 0 | 0% | 0 | Art, G&E, and equipment moves
1002 | Transportation & Meals | Mileage, fuel, parking, and local runs | allowance | 1 | 150 | 0% | 150 | No airfare, hotel, or per diem
1003 | Transportation & Meals | Catering | meals | 30 | 18 | 0% | 540 | Estimated headcount × shoot days
1004 | Transportation & Meals | Craft service / water | person-days | 30 | 6 | 0% | 180 | Continuous table-side work requires controlled food handling
1005 | Transportation & Meals | Late meal / extra-headcount reserve | allowance | 1 | 100 | 0% | 100 | Separate from payroll meal penalties
TRANSPORTATION & MEALS SUBTOTAL | [6 empty] | 970 | Account group 1000
1100 — Post-Production
1101 | Post-Production | Picture editor | workdays | 5 | 175 | 12% | 980 | Dialogue rhythm, montage, and poker inserts
1102 | Post-Production | Assistant editor | workdays | 0 | 0 | 12% | 0 | Sync, organize, turnovers, versions
1103 | Post-Production | Post storage / backup | allowance | 1 | 50 | 0% | 50 | Project and master retention
1104 | Post-Production | Color correction / grade | sessions | 1 | 200 | 0% | 200 | Protect skin tones, green felt, cards, and dark surround
1105 | Post-Production | Dialogue edit / sound design | workdays | 2 | 150 | 0% | 300 | Dialogue cleanup, cards, chips, room tone
1106 | Post-Production | Final mix | sessions | 1 | 200 | 0% | 200 | Stereo plus higher-tier 5.1 as needed
1107 | Post-Production | ADR / pickup reserve | allowance | 0 | 0 | 0% | 0 | Five-performer dialogue insurance
1108 | Post-Production | Original score / composer | flat | 1 | 200 | 0% | 200 | Original music avoids premium master-use costs
1109 | Post-Production | Music recording / library / clearance | allowance | 1 | 50 | 0% | 50 | Replace with written quotes before licensing
1110 | Post-Production | Titles, graphics, and slow-motion polish | allowance | 1 | 75 | 0% | 75 | Opening/end titles and minor cleanup
1111 | Post-Production | Online conform / mastering / QC | allowance | 1 | 100 | 0% | 100 | Picture and sound master verification
1112 | Post-Production | Captions / subtitles | allowance | 1 | 75 | 0% | 75 | English captions; foreign language versions extra
1113 | Post-Production | DCP / festival and review masters | allowance | 0 | 0 | 0% | 0 | Festival-ready package
POST-PRODUCTION SUBTOTAL | [6 empty] | 2230 | Account group 1100
1200 — Insurance / Legal / Admin / Marketing
1201 | Insurance / Legal / Admin / Marketing | Production package insurance | flat | 1 | 400 | 0% | 400 | General liability, equipment, workers comp as quoted
1202 | Insurance / Legal / Admin / Marketing | Errors & omissions insurance | flat | 0 | 0 | 0% | 0 | Often needed for distribution; quote based on rights package
1203 | Insurance / Legal / Admin / Marketing | Final legal, releases, and clearance | allowance | 1 | 100 | 0% | 100 | Cast, location, music, trademark, title, and chain of title
1204 | Insurance / Legal / Admin / Marketing | Bookkeeping / cost report / tax filing | allowance | 1 | 100 | 0% | 100 | Final cost reporting included
1205 | Insurance / Legal / Admin / Marketing | Entity, office, bank, courier, and communications | allowance | 1 | 50 | 0% | 50 | Production administration
1206 | Insurance / Legal / Admin / Marketing | Unit stills / EPK | allowance | 0 | 0 | 0% | 0 | Festival, press, and sales materials
1207 | Insurance / Legal / Admin / Marketing | Festival submissions / key art / launch reserve | allowance | 1 | 100 | 0% | 100 | Distribution spend beyond launch is excluded
1208 | Insurance / Legal / Admin / Marketing | Long-term data archive | allowance | 1 | 50 | 0% | 50 | Master, stems, project, legal, and stills archive
INSURANCE / LEGAL / ADMIN / MARKETING SUBTOTAL | [6 empty] | 800 | Account group 1200
DIRECT PRODUCTION SUBTOTAL | [6 empty] | 17387.375
PRODUCTION-COMPANY OVERHEAD |  |  |  | 1 | 17387.375 | 0% | 0 | Applied to direct production subtotal
SUBTOTAL BEFORE CONTINGENCY | [6 empty] | 17387.375
CONTINGENCY |  |  |  | 1 | 17387.375 | 3% | 521.6213 | Editable risk reserve
ESTIMATED GRAND TOTAL | [6 empty] | 17908.9963 | Gross production budget; incentives excluded

## Ultra-Low Budget
Check, Cheap, All In, or Fold — Ultra-Low Budget
Professional local crew, two shoot days plus rehearsal, controlled private-room location, stronger art/lighting/sound, continuity duplicates, complete sound/color, captions, DCP, and E&O. ¦ USD ¦ Gross budget before incentives
Scenario | Grand Total | Shoot Days | Prep Weeks | Post Weeks | Paid Props | Gross Cast | Performer Framework | Planning Note
Ultra-Low Budget | 82222.35 | 2 | 2 | 4 | 3090 | 4500 | SAG-AFTRA Ultra Low Budget Project Agreement (UPA) planning case | Professional local crew, two shoot days plus rehearsal, controlled private-room location, stronger art/lighting/sound, continuity duplicates, complete sound/color, captions, DCP, and E&O.
Labor assumptions are planning inputs, not payroll quotations. Confirm the final SAG-AFTRA agreement, state/local wage law, overtime, meal penalties, workers compensation, and any IATSE/Teamsters/DGA obligations before hiring.
No tax credit, grant, rebate, sponsorship, product placement, donated labor, or in-kind equipment reduces this gross budget. Refundable deposits and union security deposits are cash-flow needs but are not treated as final costs unless retained.
Account | Category | Line Item | Basis | Qty | Rate / Linked Base | Fringe / Load | Line Total | Notes
0100 — Development & Above-the-Line
0101 | Development & Above-the-Line | Screenplay license / writer fee | flat | 1 | 1000 | 0% | 1000 | Paid rights/fee placeholder; replace with negotiated writer/producer deal
0102 | Development & Above-the-Line | Rewrite / production polish | flat | 1 | 500 | 0% | 500 | Final continuity and production draft
0103 | Development & Above-the-Line | Producer fee | flat | 1 | 2000 | 0% | 2000 | Excludes production-company overhead below
0104 | Development & Above-the-Line | Director fee | flat | 1 | 2500 | 0% | 2500 | DGA Level 1a compensation is negotiable when applicable
0105 | Development & Above-the-Line | Casting | flat | 1 | 800 | 0% | 800 | Five speaking roles; no background casting
0106 | Development & Above-the-Line | Poker consultant / hand-continuity design | flat | 1 | 600 | 0% | 600 | Verify gameplay, prebuild hands, coach dealing and chip action
0107 | Development & Above-the-Line | Business affairs / chain-of-title prep | flat | 1 | 500 | 0% | 500 | Rights, releases, guild setup, and entity records
DEVELOPMENT & ABOVE-THE-LINE SUBTOTAL | [6 empty] | 7900 | Account group 0100
0200 — Cast
0201 | Cast | Principal performers — five paid speaking roles | linked cast gross | 1 | 4500 | 0% | 4500 | Pulled from Cast & Schedule
0202 | Cast | SAG-AFTRA pension & health | % principal gross | 1 | 4500 | 22% | 990 | Applied to gross principal payroll; Micro left at 0% pending agreement choice
0203 | Cast | Employer payroll taxes / workers comp | % principal gross | 1 | 4500 | 12% | 540 | Editable planning load
0204 | Cast | Entertainment payroll service | % principal gross | 1 | 4500 | 3% | 135 | UPA requires entertainment payroll processing
0205 | Cast | Fittings / wardrobe allowance | flat | 1 | 250 | 0% | 250 | Five contemporary looks
0206 | Cast | Local mileage, parking, and meal incidentals | flat | 1 | 400 | 0% | 400 | No airfare or lodging assumed
CAST SUBTOTAL | [6 empty] | 6815 | Account group 0200
0300 — Production Management
0301 | Production Management | Line producer / UPM | workdays | 7 | 250 | 15% | 2012.5 | Prep, production, wrap
0302 | Production Management | 1st assistant director | shoot days | 2 | 350 | 15% | 805 | Set operations and timing
0303 | Production Management | 2nd assistant director | shoot days | 2 | 225 | 15% | 517.5 | Cast flow, paperwork, and calls
0304 | Production Management | Production coordinator | workdays | 7 | 250 | 15% | 2012.5 | Call sheets, vendors, releases, wrap
0305 | Production Management | Script supervisor | shoot days | 2 | 350 | 15% | 805 | Dialogue, eyeline, card, and chip continuity
0306 | Production Management | Production assistants | person-days | 6 | 200 | 15% | 1380 | Set, lockup, runs, and strike
0307 | Production Management | Set medic / first aid | shoot days | 2 | 250 | 15% | 575 | Normal set safety coverage
0308 | Production Management | Production office / phones / printing | allowance | 1 | 400 | 0% | 400 | Digital paperwork plus essential hard copy
0309 | Production Management | Overtime / meal-penalty reserve | allowance | 1 | 500 | 0% | 500 | Separate from general contingency
PRODUCTION MANAGEMENT SUBTOTAL | [6 empty] | 9007.5 | Account group 0300
0400 — Camera
0401 | Camera | Director of photography | shoot days | 2 | 650 | 15% | 1495 | DP operates at Micro/Ultra tiers
0402 | Camera | Camera operator | shoot days | 0 | 0 | 15% | 0 | Dedicated operator at higher tiers
0403 | Camera | 1st assistant camera | shoot days | 2 | 450 | 15% | 1035 | Focus, lens changes, camera build
0404 | Camera | 2nd AC / loader | shoot days | 2 | 300 | 15% | 690 | Slates, media, reports
0405 | Camera | DIT / data wrangler | shoot days | 2 | 300 | 15% | 690 | Verified dual backups and look management
0406 | Camera | Camera and lens package | shoot days | 2 | 750 | 0% | 1500 | Camera, lenses, support, filters
0407 | Camera | Media and production backup drives | allowance | 1 | 400 | 0% | 400 | At least two verified copies
0408 | Camera | Video village / wireless monitoring | package | 1 | 300 | 0% | 300 | Director, script, and client monitoring
0409 | Camera | Dolly / slider / gimbal | package | 1 | 300 | 0% | 300 | Slow push-ins and table movement
0410 | Camera | Camera expendables | allowance | 1 | 150 | 0% | 150 | Tape, wipes, batteries, adapters
CAMERA SUBTOTAL | [6 empty] | 6560 | Account group 0400
0500 — Grip & Electric
0501 | Grip & Electric | Gaffer | shoot days | 2 | 450 | 15% | 1035 | Warm table pool and dark surround
0502 | Grip & Electric | Key grip | shoot days | 2 | 400 | 15% | 920 | Rigging, shaping, camera movement
0503 | Grip & Electric | Grip / electric swings | person-days | 4 | 300 | 15% | 1380 | Tier-scaled crew
0504 | Grip & Electric | G&E package | shoot days | 2 | 800 | 0% | 1600 | LEDs, stands, flags, rigging, distro
0505 | Grip & Electric | Power and distribution | allowance | 1 | 200 | 0% | 200 | Location-safe power plan
0506 | Grip & Electric | Practical lamp control / dimmers | allowance | 1 | 250 | 0% | 250 | Flicker-free bulbs and dimming
0507 | Grip & Electric | G&E expendables | allowance | 1 | 150 | 0% | 150 | Gel, tape, blackwrap, hardware
GRIP & ELECTRIC SUBTOTAL | [6 empty] | 5535 | Account group 0500
0600 — Production Sound
0601 | Production Sound | Production sound mixer | shoot days | 2 | 500 | 15% | 1150 | Five-character dialogue
0602 | Production Sound | Boom operator | shoot days | 2 | 300 | 15% | 690 | Mixer booms in Micro case
0603 | Production Sound | Recorder / mixer / wireless package | shoot days | 2 | 400 | 0% | 800 | Five lavs, boom, timecode by tier
0604 | Production Sound | Additional lav / timecode / IFB | allowance | 1 | 200 | 0% | 200 | Tier-scaled coverage
0605 | Production Sound | Sound expendables | allowance | 1 | 75 | 0% | 75 | Batteries, mounts, tape, windscreens
PRODUCTION SOUND SUBTOTAL | [6 empty] | 2915 | Account group 0600
0700 — Art Department & Paid Props
0701 | Art Department & Paid Props | Production designer | workdays | 5 | 350 | 15% | 2012.5 | Concept, palette, location transformation
0702 | Art Department & Paid Props | Art director / set decorator | workdays | 4 | 300 | 15% | 1380 | Sourcing, installation, returns
0703 | Art Department & Paid Props | Prop master / card continuity | workdays | 4 | 350 | 15% | 1610 | Prebuild every hand and chip state
0704 | Art Department & Paid Props | Art / props production assistant | person-days | 2 | 175 | 15% | 402.5 | Prep, resets, strike
0705 | Art Department & Paid Props | Private poker-room build and dressing | allowance | 1 | 1500 | 0% | 1500 | Wall treatment, blackout, floor protection, install/strike
0706 | Art Department & Paid Props | Paid poker props and set dressing | linked prop total | 1 | 3090 | 0% | 3090 | Pulled from Props & Art
0707 | Art Department & Paid Props | Art transport, returns, and storage | allowance | 1 | 250 | 0% | 250 | Cargo, consumables, return fees
ART DEPARTMENT & PAID PROPS SUBTOTAL | [6 empty] | 10245 | Account group 0700
0800 — Wardrobe / Hair / Makeup
0801 | Wardrobe / Hair / Makeup | Costume designer / stylist | workdays | 3 | 250 | 15% | 862.5 | Five contemporary looks
0802 | Wardrobe / Hair / Makeup | Wardrobe purchases / rentals | allowance | 1 | 800 | 0% | 800 | Character-specific pieces and backups
0803 | Wardrobe / Hair / Makeup | Alterations, laundry, and returns | allowance | 1 | 200 | 0% | 200 | Prep and wrap
0804 | Wardrobe / Hair / Makeup | Hair and makeup key | shoot days | 2 | 400 | 15% | 920 | Camera-ready continuity
0805 | Wardrobe / Hair / Makeup | Hair / makeup assistant | shoot days | 0 | 0 | 15% | 0 | Higher-tier support
0806 | Wardrobe / Hair / Makeup | Wardrobe / HMU kits and expendables | allowance | 1 | 250 | 0% | 250 | Sanitary disposables and repair supplies
WARDROBE / HAIR / MAKEUP SUBTOTAL | [6 empty] | 3032.5 | Account group 0800
0900 — Locations
0901 | Locations | Private poker room / stage | access days | 3 | 1000 | 0% | 3000 | Shoot plus prep/strike access by tier
0902 | Locations | Location manager / scout | workdays | 3 | 250 | 15% | 862.5 | Scout, contract, neighbors, logistics
0903 | Locations | Permit / film office / site representative | allowance | 1 | 500 | 0% | 500 | Jurisdiction and venue dependent
0904 | Locations | Cleaning, utilities, floor protection, damage reserve | allowance | 1 | 350 | 0% | 350 | Not the refundable security deposit itself
0905 | Locations | Parking, holding, restroom, and security | allowance | 1 | 400 | 0% | 400 | Crew/cast base support
LOCATIONS SUBTOTAL | [6 empty] | 5112.5 | Account group 0900
1000 — Transportation & Meals
1001 | Transportation & Meals | Production van / cargo vehicle | rental days | 2 | 250 | 0% | 500 | Art, G&E, and equipment moves
1002 | Transportation & Meals | Mileage, fuel, parking, and local runs | allowance | 1 | 500 | 0% | 500 | No airfare, hotel, or per diem
1003 | Transportation & Meals | Catering | meals | 44 | 28 | 0% | 1232 | Estimated headcount × shoot days
1004 | Transportation & Meals | Craft service / water | person-days | 44 | 10 | 0% | 440 | Continuous table-side work requires controlled food handling
1005 | Transportation & Meals | Late meal / extra-headcount reserve | allowance | 1 | 400 | 0% | 400 | Separate from payroll meal penalties
TRANSPORTATION & MEALS SUBTOTAL | [6 empty] | 3072 | Account group 1000
1100 — Post-Production
1101 | Post-Production | Picture editor | workdays | 10 | 400 | 15% | 4600 | Dialogue rhythm, montage, and poker inserts
1102 | Post-Production | Assistant editor | workdays | 3 | 250 | 15% | 862.5 | Sync, organize, turnovers, versions
1103 | Post-Production | Post storage / backup | allowance | 1 | 300 | 0% | 300 | Project and master retention
1104 | Post-Production | Color correction / grade | sessions | 2 | 600 | 0% | 1200 | Protect skin tones, green felt, cards, and dark surround
1105 | Post-Production | Dialogue edit / sound design | workdays | 4 | 500 | 0% | 2000 | Dialogue cleanup, cards, chips, room tone
1106 | Post-Production | Final mix | sessions | 1 | 800 | 0% | 800 | Stereo plus higher-tier 5.1 as needed
1107 | Post-Production | ADR / pickup reserve | allowance | 1 | 300 | 0% | 300 | Five-performer dialogue insurance
1108 | Post-Production | Original score / composer | flat | 1 | 1000 | 0% | 1000 | Original music avoids premium master-use costs
1109 | Post-Production | Music recording / library / clearance | allowance | 1 | 500 | 0% | 500 | Replace with written quotes before licensing
1110 | Post-Production | Titles, graphics, and slow-motion polish | allowance | 1 | 400 | 0% | 400 | Opening/end titles and minor cleanup
1111 | Post-Production | Online conform / mastering / QC | allowance | 1 | 500 | 0% | 500 | Picture and sound master verification
1112 | Post-Production | Captions / subtitles | allowance | 1 | 200 | 0% | 200 | English captions; foreign language versions extra
1113 | Post-Production | DCP / festival and review masters | allowance | 1 | 300 | 0% | 300 | Festival-ready package
POST-PRODUCTION SUBTOTAL | [6 empty] | 12962.5 | Account group 1100
1200 — Insurance / Legal / Admin / Marketing
1201 | Insurance / Legal / Admin / Marketing | Production package insurance | flat | 1 | 1200 | 0% | 1200 | General liability, equipment, workers comp as quoted
1202 | Insurance / Legal / Admin / Marketing | Errors & omissions insurance | flat | 1 | 1000 | 0% | 1000 | Often needed for distribution; quote based on rights package
1203 | Insurance / Legal / Admin / Marketing | Final legal, releases, and clearance | allowance | 1 | 750 | 0% | 750 | Cast, location, music, trademark, title, and chain of title
1204 | Insurance / Legal / Admin / Marketing | Bookkeeping / cost report / tax filing | allowance | 1 | 600 | 0% | 600 | Final cost reporting included
1205 | Insurance / Legal / Admin / Marketing | Entity, office, bank, courier, and communications | allowance | 1 | 300 | 0% | 300 | Production administration
1206 | Insurance / Legal / Admin / Marketing | Unit stills / EPK | allowance | 1 | 300 | 0% | 300 | Festival, press, and sales materials
1207 | Insurance / Legal / Admin / Marketing | Festival submissions / key art / launch reserve | allowance | 1 | 800 | 0% | 800 | Distribution spend beyond launch is excluded
1208 | Insurance / Legal / Admin / Marketing | Long-term data archive | allowance | 1 | 200 | 0% | 200 | Master, stems, project, legal, and stills archive
INSURANCE / LEGAL / ADMIN / MARKETING SUBTOTAL | [6 empty] | 5150 | Account group 1200
DIRECT PRODUCTION SUBTOTAL | [6 empty] | 78307
PRODUCTION-COMPANY OVERHEAD |  |  |  | 1 | 78307 | 0% | 0 | Applied to direct production subtotal
SUBTOTAL BEFORE CONTINGENCY | [6 empty] | 78307
CONTINGENCY |  |  |  | 1 | 78307 | 5% | 3915.35 | Editable risk reserve
ESTIMATED GRAND TOTAL | [6 empty] | 82222.35 | Gross production budget; incentives excluded

## Low Budget
Check, Cheap, All In, or Fold — Low Budget
Three-day coverage plan for a dialogue-heavy ensemble; experienced department heads; designed poker room; cinema package, dolly and video village; enhanced post, publicity, and delivery. ¦ USD ¦ Gross budget before incentives
Scenario | Grand Total | Shoot Days | Prep Weeks | Post Weeks | Paid Props | Gross Cast | Performer Framework | Planning Note
Low Budget | 246442.7852 | 3 | 3 | 6 | 6910 | 8600 | SAG-AFTRA UPA minimums with negotiated overscale performer placeholders | Three-day coverage plan for a dialogue-heavy ensemble; experienced department heads; designed poker room; cinema package, dolly and video village; enhanced post, publicity, and delivery.
Labor assumptions are planning inputs, not payroll quotations. Confirm the final SAG-AFTRA agreement, state/local wage law, overtime, meal penalties, workers compensation, and any IATSE/Teamsters/DGA obligations before hiring.
No tax credit, grant, rebate, sponsorship, product placement, donated labor, or in-kind equipment reduces this gross budget. Refundable deposits and union security deposits are cash-flow needs but are not treated as final costs unless retained.
Account | Category | Line Item | Basis | Qty | Rate / Linked Base | Fringe / Load | Line Total | Notes
0100 — Development & Above-the-Line
0101 | Development & Above-the-Line | Screenplay license / writer fee | flat | 1 | 3000 | 0% | 3000 | Paid rights/fee placeholder; replace with negotiated writer/producer deal
0102 | Development & Above-the-Line | Rewrite / production polish | flat | 1 | 1500 | 0% | 1500 | Final continuity and production draft
0103 | Development & Above-the-Line | Producer fee | flat | 1 | 6000 | 0% | 6000 | Excludes production-company overhead below
0104 | Development & Above-the-Line | Director fee | flat | 1 | 8000 | 0% | 8000 | DGA Level 1a compensation is negotiable when applicable
0105 | Development & Above-the-Line | Casting | flat | 1 | 2000 | 0% | 2000 | Five speaking roles; no background casting
0106 | Development & Above-the-Line | Poker consultant / hand-continuity design | flat | 1 | 1500 | 0% | 1500 | Verify gameplay, prebuild hands, coach dealing and chip action
0107 | Development & Above-the-Line | Business affairs / chain-of-title prep | flat | 1 | 1500 | 0% | 1500 | Rights, releases, guild setup, and entity records
DEVELOPMENT & ABOVE-THE-LINE SUBTOTAL | [6 empty] | 23500 | Account group 0100
0200 — Cast
0201 | Cast | Principal performers — five paid speaking roles | linked cast gross | 1 | 8600 | 0% | 8600 | Pulled from Cast & Schedule
0202 | Cast | SAG-AFTRA pension & health | % principal gross | 1 | 8600 | 22% | 1892 | Applied to gross principal payroll; Micro left at 0% pending agreement choice
0203 | Cast | Employer payroll taxes / workers comp | % principal gross | 1 | 8600 | 12% | 1032 | Editable planning load
0204 | Cast | Entertainment payroll service | % principal gross | 1 | 8600 | 3% | 258 | UPA requires entertainment payroll processing
0205 | Cast | Fittings / wardrobe allowance | flat | 1 | 500 | 0% | 500 | Five contemporary looks
0206 | Cast | Local mileage, parking, and meal incidentals | flat | 1 | 750 | 0% | 750 | No airfare or lodging assumed
CAST SUBTOTAL | [6 empty] | 13032 | Account group 0200
0300 — Production Management
0301 | Production Management | Line producer / UPM | workdays | 15 | 350 | 19% | 6247.5 | Prep, production, wrap
0302 | Production Management | 1st assistant director | shoot days | 3 | 550 | 19% | 1963.5 | Set operations and timing
0303 | Production Management | 2nd assistant director | shoot days | 3 | 350 | 19% | 1249.5 | Cast flow, paperwork, and calls
0304 | Production Management | Production coordinator | workdays | 12 | 350 | 19% | 4998 | Call sheets, vendors, releases, wrap
0305 | Production Management | Script supervisor | shoot days | 3 | 550 | 19% | 1963.5 | Dialogue, eyeline, card, and chip continuity
0306 | Production Management | Production assistants | person-days | 9 | 250 | 19% | 2677.5 | Set, lockup, runs, and strike
0307 | Production Management | Set medic / first aid | shoot days | 3 | 350 | 19% | 1249.5 | Normal set safety coverage
0308 | Production Management | Production office / phones / printing | allowance | 1 | 1000 | 0% | 1000 | Digital paperwork plus essential hard copy
0309 | Production Management | Overtime / meal-penalty reserve | allowance | 1 | 1500 | 0% | 1500 | Separate from general contingency
PRODUCTION MANAGEMENT SUBTOTAL | [6 empty] | 22849 | Account group 0300
0400 — Camera
0401 | Camera | Director of photography | shoot days | 3 | 1000 | 19% | 3570 | DP operates at Micro/Ultra tiers
0402 | Camera | Camera operator | shoot days | 3 | 500 | 19% | 1785 | Dedicated operator at higher tiers
0403 | Camera | 1st assistant camera | shoot days | 3 | 700 | 19% | 2499 | Focus, lens changes, camera build
0404 | Camera | 2nd AC / loader | shoot days | 3 | 450 | 19% | 1606.5 | Slates, media, reports
0405 | Camera | DIT / data wrangler | shoot days | 3 | 500 | 19% | 1785 | Verified dual backups and look management
0406 | Camera | Camera and lens package | shoot days | 3 | 1200 | 0% | 3600 | Camera, lenses, support, filters
0407 | Camera | Media and production backup drives | allowance | 1 | 900 | 0% | 900 | At least two verified copies
0408 | Camera | Video village / wireless monitoring | package | 1 | 900 | 0% | 900 | Director, script, and client monitoring
0409 | Camera | Dolly / slider / gimbal | package | 1 | 900 | 0% | 900 | Slow push-ins and table movement
0410 | Camera | Camera expendables | allowance | 1 | 300 | 0% | 300 | Tape, wipes, batteries, adapters
CAMERA SUBTOTAL | [6 empty] | 17845.5 | Account group 0400
0500 — Grip & Electric
0501 | Grip & Electric | Gaffer | shoot days | 3 | 750 | 19% | 2677.5 | Warm table pool and dark surround
0502 | Grip & Electric | Key grip | shoot days | 3 | 700 | 19% | 2499 | Rigging, shaping, camera movement
0503 | Grip & Electric | Grip / electric swings | person-days | 9 | 450 | 19% | 4819.5 | Tier-scaled crew
0504 | Grip & Electric | G&E package | shoot days | 3 | 1500 | 0% | 4500 | LEDs, stands, flags, rigging, distro
0505 | Grip & Electric | Power and distribution | allowance | 1 | 600 | 0% | 600 | Location-safe power plan
0506 | Grip & Electric | Practical lamp control / dimmers | allowance | 1 | 500 | 0% | 500 | Flicker-free bulbs and dimming
0507 | Grip & Electric | G&E expendables | allowance | 1 | 400 | 0% | 400 | Gel, tape, blackwrap, hardware
GRIP & ELECTRIC SUBTOTAL | [6 empty] | 15996 | Account group 0500
0600 — Production Sound
0601 | Production Sound | Production sound mixer | shoot days | 3 | 750 | 19% | 2677.5 | Five-character dialogue
0602 | Production Sound | Boom operator | shoot days | 3 | 500 | 19% | 1785 | Mixer booms in Micro case
0603 | Production Sound | Recorder / mixer / wireless package | shoot days | 3 | 700 | 0% | 2100 | Five lavs, boom, timecode by tier
0604 | Production Sound | Additional lav / timecode / IFB | allowance | 1 | 450 | 0% | 450 | Tier-scaled coverage
0605 | Production Sound | Sound expendables | allowance | 1 | 150 | 0% | 150 | Batteries, mounts, tape, windscreens
PRODUCTION SOUND SUBTOTAL | [6 empty] | 7162.5 | Account group 0600
0700 — Art Department & Paid Props
0701 | Art Department & Paid Props | Production designer | workdays | 10 | 550 | 19% | 6545 | Concept, palette, location transformation
0702 | Art Department & Paid Props | Art director / set decorator | workdays | 8 | 500 | 19% | 4760 | Sourcing, installation, returns
0703 | Art Department & Paid Props | Prop master / card continuity | workdays | 7 | 550 | 19% | 4581.5 | Prebuild every hand and chip state
0704 | Art Department & Paid Props | Art / props production assistant | person-days | 6 | 250 | 19% | 1785 | Prep, resets, strike
0705 | Art Department & Paid Props | Private poker-room build and dressing | allowance | 1 | 5000 | 0% | 5000 | Wall treatment, blackout, floor protection, install/strike
0706 | Art Department & Paid Props | Paid poker props and set dressing | linked prop total | 1 | 6910 | 0% | 6910 | Pulled from Props & Art
0707 | Art Department & Paid Props | Art transport, returns, and storage | allowance | 1 | 750 | 0% | 750 | Cargo, consumables, return fees
ART DEPARTMENT & PAID PROPS SUBTOTAL | [6 empty] | 30331.5 | Account group 0700
0800 — Wardrobe / Hair / Makeup
0801 | Wardrobe / Hair / Makeup | Costume designer / stylist | workdays | 6 | 450 | 19% | 3213 | Five contemporary looks
0802 | Wardrobe / Hair / Makeup | Wardrobe purchases / rentals | allowance | 1 | 2000 | 0% | 2000 | Character-specific pieces and backups
0803 | Wardrobe / Hair / Makeup | Alterations, laundry, and returns | allowance | 1 | 500 | 0% | 500 | Prep and wrap
0804 | Wardrobe / Hair / Makeup | Hair and makeup key | shoot days | 3 | 650 | 19% | 2320.5 | Camera-ready continuity
0805 | Wardrobe / Hair / Makeup | Hair / makeup assistant | shoot days | 3 | 300 | 19% | 1071 | Higher-tier support
0806 | Wardrobe / Hair / Makeup | Wardrobe / HMU kits and expendables | allowance | 1 | 600 | 0% | 600 | Sanitary disposables and repair supplies
WARDROBE / HAIR / MAKEUP SUBTOTAL | [6 empty] | 9704.5 | Account group 0800
0900 — Locations
0901 | Locations | Private poker room / stage | access days | 5 | 1600 | 0% | 8000 | Shoot plus prep/strike access by tier
0902 | Locations | Location manager / scout | workdays | 6 | 450 | 19% | 3213 | Scout, contract, neighbors, logistics
0903 | Locations | Permit / film office / site representative | allowance | 1 | 1500 | 0% | 1500 | Jurisdiction and venue dependent
0904 | Locations | Cleaning, utilities, floor protection, damage reserve | allowance | 1 | 1000 | 0% | 1000 | Not the refundable security deposit itself
0905 | Locations | Parking, holding, restroom, and security | allowance | 1 | 1200 | 0% | 1200 | Crew/cast base support
LOCATIONS SUBTOTAL | [6 empty] | 14913 | Account group 0900
1000 — Transportation & Meals
1001 | Transportation & Meals | Production van / cargo vehicle | rental days | 4 | 400 | 0% | 1600 | Art, G&E, and equipment moves
1002 | Transportation & Meals | Mileage, fuel, parking, and local runs | allowance | 1 | 1200 | 0% | 1200 | No airfare, hotel, or per diem
1003 | Transportation & Meals | Catering | meals | 90 | 40 | 0% | 3600 | Estimated headcount × shoot days
1004 | Transportation & Meals | Craft service / water | person-days | 90 | 15 | 0% | 1350 | Continuous table-side work requires controlled food handling
1005 | Transportation & Meals | Late meal / extra-headcount reserve | allowance | 1 | 1200 | 0% | 1200 | Separate from payroll meal penalties
TRANSPORTATION & MEALS SUBTOTAL | [6 empty] | 8950 | Account group 1000
1100 — Post-Production
1101 | Post-Production | Picture editor | workdays | 20 | 650 | 19% | 15470 | Dialogue rhythm, montage, and poker inserts
1102 | Post-Production | Assistant editor | workdays | 8 | 400 | 19% | 3808 | Sync, organize, turnovers, versions
1103 | Post-Production | Post storage / backup | allowance | 1 | 900 | 0% | 900 | Project and master retention
1104 | Post-Production | Color correction / grade | sessions | 3 | 1500 | 0% | 4500 | Protect skin tones, green felt, cards, and dark surround
1105 | Post-Production | Dialogue edit / sound design | workdays | 8 | 800 | 0% | 6400 | Dialogue cleanup, cards, chips, room tone
1106 | Post-Production | Final mix | sessions | 2 | 1500 | 0% | 3000 | Stereo plus higher-tier 5.1 as needed
1107 | Post-Production | ADR / pickup reserve | allowance | 1 | 750 | 0% | 750 | Five-performer dialogue insurance
1108 | Post-Production | Original score / composer | flat | 1 | 3500 | 0% | 3500 | Original music avoids premium master-use costs
1109 | Post-Production | Music recording / library / clearance | allowance | 1 | 1500 | 0% | 1500 | Replace with written quotes before licensing
1110 | Post-Production | Titles, graphics, and slow-motion polish | allowance | 1 | 1200 | 0% | 1200 | Opening/end titles and minor cleanup
1111 | Post-Production | Online conform / mastering / QC | allowance | 1 | 1500 | 0% | 1500 | Picture and sound master verification
1112 | Post-Production | Captions / subtitles | allowance | 1 | 500 | 0% | 500 | English captions; foreign language versions extra
1113 | Post-Production | DCP / festival and review masters | allowance | 1 | 1000 | 0% | 1000 | Festival-ready package
POST-PRODUCTION SUBTOTAL | [6 empty] | 44028 | Account group 1100
1200 — Insurance / Legal / Admin / Marketing
1201 | Insurance / Legal / Admin / Marketing | Production package insurance | flat | 1 | 3500 | 0% | 3500 | General liability, equipment, workers comp as quoted
1202 | Insurance / Legal / Admin / Marketing | Errors & omissions insurance | flat | 1 | 3000 | 0% | 3000 | Often needed for distribution; quote based on rights package
1203 | Insurance / Legal / Admin / Marketing | Final legal, releases, and clearance | allowance | 1 | 2000 | 0% | 2000 | Cast, location, music, trademark, title, and chain of title
1204 | Insurance / Legal / Admin / Marketing | Bookkeeping / cost report / tax filing | allowance | 1 | 1800 | 0% | 1800 | Final cost reporting included
1205 | Insurance / Legal / Admin / Marketing | Entity, office, bank, courier, and communications | allowance | 1 | 800 | 0% | 800 | Production administration
1206 | Insurance / Legal / Admin / Marketing | Unit stills / EPK | allowance | 1 | 1200 | 0% | 1200 | Festival, press, and sales materials
1207 | Insurance / Legal / Admin / Marketing | Festival submissions / key art / launch reserve | allowance | 1 | 2500 | 0% | 2500 | Distribution spend beyond launch is excluded
1208 | Insurance / Legal / Admin / Marketing | Long-term data archive | allowance | 1 | 500 | 0% | 500 | Master, stems, project, legal, and stills archive
INSURANCE / LEGAL / ADMIN / MARKETING SUBTOTAL | [6 empty] | 15300 | Account group 1200
DIRECT PRODUCTION SUBTOTAL | [6 empty] | 223612
PRODUCTION-COMPANY OVERHEAD |  |  |  | 1 | 223612 | 3% | 6708.36 | Applied to direct production subtotal
SUBTOTAL BEFORE CONTINGENCY | [6 empty] | 230320.36
CONTINGENCY |  |  |  | 1 | 230320.36 | 7% | 16122.4252 | Editable risk reserve
ESTIMATED GRAND TOTAL | [6 empty] | 246442.7852 | Gross production budget; incentives excluded

## Production Co
Check, Cheap, All In, or Fold — Production Company
Production-company execution with overscale cast, staffed departments, stage/control days, custom poker-room finish, premium equipment, full editorial/sound/color pipeline, EPK, legal, and distribution-ready masters. ¦ USD ¦ Gross budget before incentives
Scenario | Grand Total | Shoot Days | Prep Weeks | Post Weeks | Paid Props | Gross Cast | Performer Framework | Planning Note
Production Company | 592679.8458 | 4 | 5 | 8 | 14450 | 23650 | SAG-AFTRA Moderate Low Budget (MPA) / DGA Level 1a planning framework | Production-company execution with overscale cast, staffed departments, stage/control days, custom poker-room finish, premium equipment, full editorial/sound/color pipeline, EPK, legal, and distribution-ready masters.
Labor assumptions are planning inputs, not payroll quotations. Confirm the final SAG-AFTRA agreement, state/local wage law, overtime, meal penalties, workers compensation, and any IATSE/Teamsters/DGA obligations before hiring.
No tax credit, grant, rebate, sponsorship, product placement, donated labor, or in-kind equipment reduces this gross budget. Refundable deposits and union security deposits are cash-flow needs but are not treated as final costs unless retained.
Account | Category | Line Item | Basis | Qty | Rate / Linked Base | Fringe / Load | Line Total | Notes
0100 — Development & Above-the-Line
0101 | Development & Above-the-Line | Screenplay license / writer fee | flat | 1 | 8000 | 0% | 8000 | Paid rights/fee placeholder; replace with negotiated writer/producer deal
0102 | Development & Above-the-Line | Rewrite / production polish | flat | 1 | 4000 | 0% | 4000 | Final continuity and production draft
0103 | Development & Above-the-Line | Producer fee | flat | 1 | 15000 | 0% | 15000 | Excludes production-company overhead below
0104 | Development & Above-the-Line | Director fee | flat | 1 | 20000 | 0% | 20000 | DGA Level 1a compensation is negotiable when applicable
0105 | Development & Above-the-Line | Casting | flat | 1 | 5000 | 0% | 5000 | Five speaking roles; no background casting
0106 | Development & Above-the-Line | Poker consultant / hand-continuity design | flat | 1 | 4000 | 0% | 4000 | Verify gameplay, prebuild hands, coach dealing and chip action
0107 | Development & Above-the-Line | Business affairs / chain-of-title prep | flat | 1 | 4000 | 0% | 4000 | Rights, releases, guild setup, and entity records
DEVELOPMENT & ABOVE-THE-LINE SUBTOTAL | [6 empty] | 60000 | Account group 0100
0200 — Cast
0201 | Cast | Principal performers — five paid speaking roles | linked cast gross | 1 | 23650 | 0% | 23650 | Pulled from Cast & Schedule
0202 | Cast | SAG-AFTRA pension & health | % principal gross | 1 | 23650 | 22% | 5203 | Applied to gross principal payroll; Micro left at 0% pending agreement choice
0203 | Cast | Employer payroll taxes / workers comp | % principal gross | 1 | 23650 | 12% | 2838 | Editable planning load
0204 | Cast | Entertainment payroll service | % principal gross | 1 | 23650 | 3.5% | 827.75 | UPA requires entertainment payroll processing
0205 | Cast | Fittings / wardrobe allowance | flat | 1 | 1250 | 0% | 1250 | Five contemporary looks
0206 | Cast | Local mileage, parking, and meal incidentals | flat | 1 | 1500 | 0% | 1500 | No airfare or lodging assumed
CAST SUBTOTAL | [6 empty] | 35268.75 | Account group 0200
0300 — Production Management
0301 | Production Management | Line producer / UPM | workdays | 20 | 600 | 24% | 14880 | Prep, production, wrap
0302 | Production Management | 1st assistant director | shoot days | 4 | 800 | 24% | 3968 | Set operations and timing
0303 | Production Management | 2nd assistant director | shoot days | 4 | 500 | 24% | 2480 | Cast flow, paperwork, and calls
0304 | Production Management | Production coordinator | workdays | 18 | 500 | 24% | 11160 | Call sheets, vendors, releases, wrap
0305 | Production Management | Script supervisor | shoot days | 4 | 700 | 24% | 3472 | Dialogue, eyeline, card, and chip continuity
0306 | Production Management | Production assistants | person-days | 12 | 325 | 24% | 4836 | Set, lockup, runs, and strike
0307 | Production Management | Set medic / first aid | shoot days | 4 | 500 | 24% | 2480 | Normal set safety coverage
0308 | Production Management | Production office / phones / printing | allowance | 1 | 2000 | 0% | 2000 | Digital paperwork plus essential hard copy
0309 | Production Management | Overtime / meal-penalty reserve | allowance | 1 | 4000 | 0% | 4000 | Separate from general contingency
PRODUCTION MANAGEMENT SUBTOTAL | [6 empty] | 49276 | Account group 0300
0400 — Camera
0401 | Camera | Director of photography | shoot days | 4 | 1500 | 24% | 7440 | DP operates at Micro/Ultra tiers
0402 | Camera | Camera operator | shoot days | 4 | 800 | 24% | 3968 | Dedicated operator at higher tiers
0403 | Camera | 1st assistant camera | shoot days | 4 | 900 | 24% | 4464 | Focus, lens changes, camera build
0404 | Camera | 2nd AC / loader | shoot days | 4 | 600 | 24% | 2976 | Slates, media, reports
0405 | Camera | DIT / data wrangler | shoot days | 4 | 700 | 24% | 3472 | Verified dual backups and look management
0406 | Camera | Camera and lens package | shoot days | 4 | 2500 | 0% | 10000 | Camera, lenses, support, filters
0407 | Camera | Media and production backup drives | allowance | 1 | 2000 | 0% | 2000 | At least two verified copies
0408 | Camera | Video village / wireless monitoring | package | 1 | 2200 | 0% | 2200 | Director, script, and client monitoring
0409 | Camera | Dolly / slider / gimbal | package | 1 | 2000 | 0% | 2000 | Slow push-ins and table movement
0410 | Camera | Camera expendables | allowance | 1 | 600 | 0% | 600 | Tape, wipes, batteries, adapters
CAMERA SUBTOTAL | [6 empty] | 39120 | Account group 0400
0500 — Grip & Electric
0501 | Grip & Electric | Gaffer | shoot days | 4 | 1000 | 24% | 4960 | Warm table pool and dark surround
0502 | Grip & Electric | Key grip | shoot days | 4 | 900 | 24% | 4464 | Rigging, shaping, camera movement
0503 | Grip & Electric | Grip / electric swings | person-days | 12 | 600 | 24% | 8928 | Tier-scaled crew
0504 | Grip & Electric | G&E package | shoot days | 4 | 3000 | 0% | 12000 | LEDs, stands, flags, rigging, distro
0505 | Grip & Electric | Power and distribution | allowance | 1 | 1500 | 0% | 1500 | Location-safe power plan
0506 | Grip & Electric | Practical lamp control / dimmers | allowance | 1 | 1000 | 0% | 1000 | Flicker-free bulbs and dimming
0507 | Grip & Electric | G&E expendables | allowance | 1 | 800 | 0% | 800 | Gel, tape, blackwrap, hardware
GRIP & ELECTRIC SUBTOTAL | [6 empty] | 33652 | Account group 0500
0600 — Production Sound
0601 | Production Sound | Production sound mixer | shoot days | 4 | 1000 | 24% | 4960 | Five-character dialogue
0602 | Production Sound | Boom operator | shoot days | 4 | 700 | 24% | 3472 | Mixer booms in Micro case
0603 | Production Sound | Recorder / mixer / wireless package | shoot days | 4 | 1200 | 0% | 4800 | Five lavs, boom, timecode by tier
0604 | Production Sound | Additional lav / timecode / IFB | allowance | 1 | 1000 | 0% | 1000 | Tier-scaled coverage
0605 | Production Sound | Sound expendables | allowance | 1 | 300 | 0% | 300 | Batteries, mounts, tape, windscreens
PRODUCTION SOUND SUBTOTAL | [6 empty] | 14532 | Account group 0600
0700 — Art Department & Paid Props
0701 | Art Department & Paid Props | Production designer | workdays | 15 | 800 | 24% | 14880 | Concept, palette, location transformation
0702 | Art Department & Paid Props | Art director / set decorator | workdays | 12 | 700 | 24% | 10416 | Sourcing, installation, returns
0703 | Art Department & Paid Props | Prop master / card continuity | workdays | 10 | 800 | 24% | 9920 | Prebuild every hand and chip state
0704 | Art Department & Paid Props | Art / props production assistant | person-days | 8 | 350 | 24% | 3472 | Prep, resets, strike
0705 | Art Department & Paid Props | Private poker-room build and dressing | allowance | 1 | 15000 | 0% | 15000 | Wall treatment, blackout, floor protection, install/strike
0706 | Art Department & Paid Props | Paid poker props and set dressing | linked prop total | 1 | 14450 | 0% | 14450 | Pulled from Props & Art
0707 | Art Department & Paid Props | Art transport, returns, and storage | allowance | 1 | 2000 | 0% | 2000 | Cargo, consumables, return fees
ART DEPARTMENT & PAID PROPS SUBTOTAL | [6 empty] | 70138 | Account group 0700
0800 — Wardrobe / Hair / Makeup
0801 | Wardrobe / Hair / Makeup | Costume designer / stylist | workdays | 8 | 650 | 24% | 6448 | Five contemporary looks
0802 | Wardrobe / Hair / Makeup | Wardrobe purchases / rentals | allowance | 1 | 5000 | 0% | 5000 | Character-specific pieces and backups
0803 | Wardrobe / Hair / Makeup | Alterations, laundry, and returns | allowance | 1 | 1200 | 0% | 1200 | Prep and wrap
0804 | Wardrobe / Hair / Makeup | Hair and makeup key | shoot days | 4 | 850 | 24% | 4216 | Camera-ready continuity
0805 | Wardrobe / Hair / Makeup | Hair / makeup assistant | shoot days | 4 | 500 | 24% | 2480 | Higher-tier support
0806 | Wardrobe / Hair / Makeup | Wardrobe / HMU kits and expendables | allowance | 1 | 1200 | 0% | 1200 | Sanitary disposables and repair supplies
WARDROBE / HAIR / MAKEUP SUBTOTAL | [6 empty] | 20544 | Account group 0800
0900 — Locations
0901 | Locations | Private poker room / stage | access days | 8 | 3000 | 0% | 24000 | Shoot plus prep/strike access by tier
0902 | Locations | Location manager / scout | workdays | 10 | 700 | 24% | 8680 | Scout, contract, neighbors, logistics
0903 | Locations | Permit / film office / site representative | allowance | 1 | 4000 | 0% | 4000 | Jurisdiction and venue dependent
0904 | Locations | Cleaning, utilities, floor protection, damage reserve | allowance | 1 | 3000 | 0% | 3000 | Not the refundable security deposit itself
0905 | Locations | Parking, holding, restroom, and security | allowance | 1 | 3000 | 0% | 3000 | Crew/cast base support
LOCATIONS SUBTOTAL | [6 empty] | 42680 | Account group 0900
1000 — Transportation & Meals
1001 | Transportation & Meals | Production van / cargo vehicle | rental days | 6 | 600 | 0% | 3600 | Art, G&E, and equipment moves
1002 | Transportation & Meals | Mileage, fuel, parking, and local runs | allowance | 1 | 2500 | 0% | 2500 | No airfare, hotel, or per diem
1003 | Transportation & Meals | Catering | meals | 160 | 55 | 0% | 8800 | Estimated headcount × shoot days
1004 | Transportation & Meals | Craft service / water | person-days | 160 | 22 | 0% | 3520 | Continuous table-side work requires controlled food handling
1005 | Transportation & Meals | Late meal / extra-headcount reserve | allowance | 1 | 3000 | 0% | 3000 | Separate from payroll meal penalties
TRANSPORTATION & MEALS SUBTOTAL | [6 empty] | 21420 | Account group 1000
1100 — Post-Production
1101 | Post-Production | Picture editor | workdays | 25 | 1000 | 24% | 31000 | Dialogue rhythm, montage, and poker inserts
1102 | Post-Production | Assistant editor | workdays | 12 | 550 | 24% | 8184 | Sync, organize, turnovers, versions
1103 | Post-Production | Post storage / backup | allowance | 1 | 2000 | 0% | 2000 | Project and master retention
1104 | Post-Production | Color correction / grade | sessions | 4 | 2500 | 0% | 10000 | Protect skin tones, green felt, cards, and dark surround
1105 | Post-Production | Dialogue edit / sound design | workdays | 12 | 1000 | 0% | 12000 | Dialogue cleanup, cards, chips, room tone
1106 | Post-Production | Final mix | sessions | 2 | 3000 | 0% | 6000 | Stereo plus higher-tier 5.1 as needed
1107 | Post-Production | ADR / pickup reserve | allowance | 1 | 2000 | 0% | 2000 | Five-performer dialogue insurance
1108 | Post-Production | Original score / composer | flat | 1 | 9000 | 0% | 9000 | Original music avoids premium master-use costs
1109 | Post-Production | Music recording / library / clearance | allowance | 1 | 3500 | 0% | 3500 | Replace with written quotes before licensing
1110 | Post-Production | Titles, graphics, and slow-motion polish | allowance | 1 | 3000 | 0% | 3000 | Opening/end titles and minor cleanup
1111 | Post-Production | Online conform / mastering / QC | allowance | 1 | 3500 | 0% | 3500 | Picture and sound master verification
1112 | Post-Production | Captions / subtitles | allowance | 1 | 1200 | 0% | 1200 | English captions; foreign language versions extra
1113 | Post-Production | DCP / festival and review masters | allowance | 1 | 2500 | 0% | 2500 | Festival-ready package
POST-PRODUCTION SUBTOTAL | [6 empty] | 93884 | Account group 1100
1200 — Insurance / Legal / Admin / Marketing
1201 | Insurance / Legal / Admin / Marketing | Production package insurance | flat | 1 | 8000 | 0% | 8000 | General liability, equipment, workers comp as quoted
1202 | Insurance / Legal / Admin / Marketing | Errors & omissions insurance | flat | 1 | 6500 | 0% | 6500 | Often needed for distribution; quote based on rights package
1203 | Insurance / Legal / Admin / Marketing | Final legal, releases, and clearance | allowance | 1 | 5000 | 0% | 5000 | Cast, location, music, trademark, title, and chain of title
1204 | Insurance / Legal / Admin / Marketing | Bookkeeping / cost report / tax filing | allowance | 1 | 4000 | 0% | 4000 | Final cost reporting included
1205 | Insurance / Legal / Admin / Marketing | Entity, office, bank, courier, and communications | allowance | 1 | 2000 | 0% | 2000 | Production administration
1206 | Insurance / Legal / Admin / Marketing | Unit stills / EPK | allowance | 1 | 3500 | 0% | 3500 | Festival, press, and sales materials
1207 | Insurance / Legal / Admin / Marketing | Festival submissions / key art / launch reserve | allowance | 1 | 7000 | 0% | 7000 | Distribution spend beyond launch is excluded
1208 | Insurance / Legal / Admin / Marketing | Long-term data archive | allowance | 1 | 1200 | 0% | 1200 | Master, stems, project, legal, and stills archive
INSURANCE / LEGAL / ADMIN / MARKETING SUBTOTAL | [6 empty] | 37200 | Account group 1200
DIRECT PRODUCTION SUBTOTAL | [6 empty] | 517714.75
PRODUCTION-COMPANY OVERHEAD |  |  |  | 1 | 517714.75 | 6% | 31062.885 | Applied to direct production subtotal
SUBTOTAL BEFORE CONTINGENCY | [6 empty] | 548777.635
CONTINGENCY |  |  |  | 1 | 548777.635 | 8% | 43902.2108 | Editable risk reserve
ESTIMATED GRAND TOTAL | [6 empty] | 592679.8458 | Gross production budget; incentives excluded

## Sources & Checks
Sources, Audit Checks & Limitations
Official contract references are current as of 2026-08-15; final payroll and guild terms require production-specific confirmation
MODEL STATUS
PASS
Check | Actual | Expected / Limit | Tolerance | Status | Notes
Micro budget is within Micro-Budget cap | 17908.9963 | 20000 | 0 | OK | SAG-AFTRA Micro-Budget cap is $20,000 per picture
Ultra-Low budget is within UPA cap | 82222.35 | 300000 | 0 | OK | UPA maximum budget is $300,000
Low budget is within UPA cap | 246442.7852 | 300000 | 0 | OK | UPA maximum budget is $300,000
Production Co budget is within MPA cap | 592679.8458 | 700000 | 0 | OK | MPA maximum budget is $700,000
Micro paid props are positive | 1050 | 0 | 0 | OK | No free-prop assumption
Ultra-Low paid props are positive | 3090 | 0 | 0 | OK | No free-prop assumption
Low paid props are positive | 6910 | 0 | 0 | OK | No free-prop assumption
Production Co paid props are positive | 14450 | 0 | 0 | OK | No free-prop assumption
Micro summary ties to budget | 0 | 0 | 0.01 | OK | Summary-to-detail tie-out
Ultra-Low summary ties to budget | 0 | 0 | 0.01 | OK | Summary-to-detail tie-out
Low summary ties to budget | 0 | 0 | 0.01 | OK | Summary-to-detail tie-out
Production Co summary ties to budget | 0 | 0 | 0.01 | OK | Summary-to-detail tie-out
All five speaking roles are budgeted | 5 | 5 | 0 | OK | Chip, Kennedy, Kimber, Miles, Holden
All prop ledger rows carry paid values | 56 | 56 | 0 | OK | 14 asset rows × 4 budget tiers
Tax incentives are excluded | 4 | 4 | 0 | OK | Gross-budget convention
Runtime input is positive | 15 | 0 | 0 | OK | Supports budget-per-minute outputs
Sources
Item | Value / Use | Units / Period | Source Type | Source Name | URL / Reference | Accessed | Notes
Screenplay | Production breakdown | Current attachment | Primary | Pasted text(20260816-042352).txt | Local attachment supplied by user | 2026-08-15 | One location; five speaking roles; contemporary poker-room short
Micro-Budget cap | $20,000 maximum | Per picture / episode | Primary | SAG-AFTRA Micro-Budget Project Agreement | https://www.sagaftra.org/production-center/contract/967/getting-started | 2026-08-15 | Most compensation terms negotiated; eligibility depends on exhibition and other restrictions
UPA cap | $300,000 maximum | Per film | Primary | SAG-AFTRA Ultra Low Budget Project | https://www.sagaftra.org/production-center/contract/819/getting-started | 2026-08-15 | Shoot entirely in the United States
UPA performer rate | $257/day | 2026-07-01 to 2027-06-30 | Primary | 2026 UPA Rate Sheet | https://www.sagaftra.org/sites/default/files/2025-10/Current%20Ultra%20Low%20Budget%20Project%20Agreement%20%28UPA%29%20Rate%20Sheet.pdf | 2026-08-15 | 20% of Basic Agreement day rate; P&H 22% effective 2026-09-06
MPA cap | $700,000 maximum | Per film | Primary | SAG-AFTRA Moderate Low Budget Project | https://www.sagaftra.org/production-center/contract/815/getting-started | 2026-08-15 | Casting incentives can alter qualifying ceiling; not assumed
MPA performer rate | $449/day | 2026-07-01 to 2027-06-30 | Primary | 2026 MPA Rate Sheet | https://www.sagaftra.org/sites/default/files/2025-10/Current%20Moderate%20Low%20Budget%20Project%20Agreement%20%28MPA%29%20Rate%20Sheet.pdf | 2026-08-15 | 35% of Basic Agreement day rate; P&H 22% effective 2026-09-06
SPA reference | $50,000 cap / 40 min max | Current | Primary | SAG-AFTRA Short Project Agreement | https://www.sagaftra.org/production-center/contract/886/getting-started | 2026-08-15 | Not the selected Ultra-Low case because that scenario may exceed the SPA cap
SPA deferred floor | $257/day principal | Subsequent-use trigger | Primary | 2026 SPA Rate Sheet | https://www.sagaftra.org/sites/default/files/2026-06/Current%20Short%20Project%20Agreement%20%28SPA%29%20Rate%20Sheet.pdf | 2026-08-15 | Initial compensation is negotiated; sheet explains deferred minimum upon subsequent use
DGA low-budget context | Level 1a compensation negotiable | Budgets through $500,000 | Primary | DGA Low Budget Sideletter / FAQ | https://www.dga.org/The-Guild/Committees/Special/Independent/FAQ | 2026-08-15 | Confirm staffing, P&H, and project/release eligibility directly with DGA
Crew, rentals, props, location, post | Planning estimates | 2026 USD | Assumption | Producer budgeting assumptions | Obtain local written bids | 2026-08-15 | Rates vary materially by city, union status, vendor, schedule, availability, and tax
Limitations and exclusions
This workbook is a financing and production-planning estimate, not a union determination, payroll quote, legal opinion, insurance binder, vendor bid, or guarantee of final cost.
No travel, lodging, per diem, premium music masters, celebrity cast, hazardous stunts, minors, animals, weapons, vehicles, visual-effects sequences, or background performers are assumed because the screenplay does not require them.
Distribution expenses beyond a modest festival/key-art reserve, residuals triggered by release, sales-agent commissions, investor fees, financing interest, and recoupment waterfalls are excluded.
Refundable location/equipment deposits and SAG-AFTRA security deposits may create temporary cash-flow needs even when they are not final production expenses.
Before greenlight, obtain a location-specific schedule and bids from payroll, insurance, legal, camera, G&E, sound, art/props, wardrobe/HMU, post, and the applicable guilds.