## Summary
Uncertain Eyes — Four One-Hour TV Budget Options
Script-specific, formula-driven planning budgets. Every tier pays cast, crew, props, rentals, safety, post, insurance and contingency. Lower tiers require the stated production compromises.
Scenario | Total budget | Shoot days | Budget / shoot day | Core approach | Performer framework | Planning note | Scenario | Total budget
Micro Budget | 223160.633 | 9 | 24795.6259 | Nine-day regional shoot; 18+ actors play teens; hospital is one redressable practical; one school campus; crash is insert-led with stunt supervision; scripted premium songs are replaced. | SAG-AFTRA Special New Media Category A only if episodic/new-media eligible and total remains under $300,000 | The SAG-AFTRA Micro-Budget Project Agreement cap is $20,000 and is not viable for this script; this label is colloquial, and Category A eligibility is conditional. | Micro Budget | 223160.633
Ultra-Low Budget | 600218.8237 | 12 | 50018.2353 | Twelve-day independent shoot; controlled bicycle stunt day; fuller hospital coverage; limited period background; combined departments; library/original music with a small source allowance. | SAG-AFTRA Special New Media Category B only if episodic/new-media eligible and total remains under $700,000 | If the live total reaches $700,000, Category B no longer fits; rebudget under Category C or full television terms. | Ultra-Low Budget | 600218.8237
Low Budget | 1450727.6986 | 15 | 96715.1799 | Fifteen-day low-budget television execution; union-scale cast; dedicated art, wardrobe and prosthetics; more period vehicles/background; original score and quoted selective source music. | Full 2026 SAG-AFTRA Television rates assumed because this case is expected to exceed the $1,000,000 Special New Media ceiling | This tier intentionally assumes full television performer rates rather than trying to force the production below the $1,000,000 Category C ceiling. | Low Budget | 1450727.6986
Production Company | 4185385.8454 | 20 | 209269.2923 | Twenty-day production-company plan; full department staffing; stronger period build and crowd scope; separate stunt/medical-effects work; age-authentic minors possible; full broadcast/streaming delivery package. | SAG-AFTRA Television plus DGA/IATSE/Teamsters terms as applicable; lead and key creative fees include negotiated overscale placeholders | A likely independent production-company negative-cost plan; network/studio overhead, financing interest and marketing remain excluded. | Production Company | 4185385.8454
Key cost driver | Micro | Ultra-low | Low | Production co.
Paid cast payroll | 22702 | 62305 | 167900.5 | 343650
Paid screenplay props | 8575 | 23525 | 59200 | 153900
Art Department & Props subtotal | 22475 | 62450 | 158825 | 444100
Wardrobe, Hair & Makeup subtotal | 14800 | 36400 | 92250 | 243500
Stunts, Medical Effects & Safety subtotal | 8149 | 17315 | 34981 | 82000
Post-Production subtotal | 22200 | 55975 | 129625 | 329000
Music subtotal | 3000 | 8800 | 23600 | 224000
Included, excluded and decision points
Included | Paid props and duplicates | Paid cast/crew and payroll loads | Locations and picture vehicles | Stunts, medical effects and safety | Post, music and delivery | Insurance and contingency
Excluded | Distributor marketing / P&A | Financing interest and lender fees | Backend participations and future residuals | Premium star quotes | Tax incentive bridge costs | Network/studio corporate overhead beyond shown allowance
Rights caveat | Life-story / participant releases | Trademark and archival review | Music master and publishing | Location and artwork releases | Minor releases and work permits | All require executed documentation
Micro reality | Rewrite and combine sets | 18+ cast for teens | Very small background groups | Replace all premium songs | Stock/VFX wildlife | High schedule pressure
Low-budget reality | Full performer rates assumed | Dedicated prosthetic and art prep | Still one regional production base | Selective source music only | No studio marketing spend | Final union review required
Production-company reality | Preserves all story blocks | Can use age-authentic minors | Fuller 1970s crowds and vehicles | Larger music allowance | Broadcast/streaming delivery | Still a planning model, not bids

## Assumptions
Uncertain Eyes — One-Hour TV Budget Assumptions
USD planning model dated 2026-08-15. Blue text/yellow fill marks editable assumptions; green text marks workbook links. Final guild agreement depends on first exhibition, signatory status and approved budget.
Section | Driver | Units | Micro Budget | Ultra-Low Budget | Low Budget | Production Company | Basis / caution
Schedule | Principal photography | days | 9 | 12 | 15 | 20 | Company moves are minimized through redresses and block shooting
Schedule | Prep | weeks | 3 | 5 | 7 | 10 | Includes safety, prosthetic and picture-vehicle prep
Schedule | Post-production | weeks | 8 | 12 | 16 | 24 | Editorial may overlap production
Labor | Illustrative performer framework | text | SAG-AFTRA Special New Media Category A only if episodic/new-media eligible and total remains under $300,000 | SAG-AFTRA Special New Media Category B only if episodic/new-media eligible and total remains under $700,000 | Full 2026 SAG-AFTRA Television rates assumed because this case is expected to exceed the $1,000,000 Special New Media ceiling | SAG-AFTRA Television plus DGA/IATSE/Teamsters terms as applicable; lead and key creative fees include negotiated overscale placeholders | Confirm directly with SAG-AFTRA before offers
Labor | Principal performer reference | $/day | 257 | 449 | 1283 | 1283 | 2026–27 current minimum reference; negotiated overscale appears in Cast & Schedule
Labor | Principal weekly reference | $/week | 0 | 1560 | 4455 | 4455 | Category A is day-rate only; full TV weekly reference derived from current scale
Labor | Background reference | $/day | 173 | 231 | 231 | 231 | Coverage and zone rules vary
Labor | Cast pension & health | % cast payroll | 21.5% | 21.5% | 21.5% | 21.5% | 21.5% planning rate from current Special New Media sheets; confirm ceilings and allocation
Labor | Crew payroll burden | % crew payroll | 11% | 14% | 18% | 23% | Planning load for payroll taxes, workers compensation and applicable benefits
Labor | Payroll company fee | % cast + crew payroll | 2.5% | 2.5% | 3% | 3.5% | Editable estimate
Risk | Contingency | % pre-contingency | 4.5% | 5% | 6.5% | 8.5% | Period exteriors, stunts, medical effects and weather drive risk
Risk | Completion bond | % pre-bond subtotal | 0% | 0% | 0% | 2% | Included only in the production-company case
Casting | Teen strategy | approach | 18+ to play younger | 18+ to play younger | Primarily 18+; limited minors | Age-authentic minors permitted | Minor rules, school time and welfare staffing can affect the schedule
Music | The Archies / Pink Floyd / Led Zeppelin | approach | Replace | Replace / quote one | Selective quotes | Clearance allowance | No scripted commercial song is assumed cleared until master and publishing licenses are signed
Incentives | Tax credits / grants | netted? | No | No | No | No | All totals are gross negative cost before incentives
Color legend
Blue text / yellow fill | Editable input | [5 empty] | Changeable planning assumption
Green text | Internal link | [5 empty] | Formula references another worksheet
Black text | Calculation / label | [5 empty] | Model output or fixed description

## Script Breakdown
One-Hour Screenplay Production Breakdown
Derived from the attached 11,266-word screenplay text. The paste contains 54 slug lines; pagination and locked scene numbers were not preserved, so a final Movie Magic stripboard is still required.
Metric | Observed / estimated | Budget implication | Planning treatment
Format | One-hour period television drama | Dense one-hour schedule with substantial company moves | Budgeted as one standalone episode/pilot
Text length | 11,266 words | Approximately 55–65 formatted screenplay pages | Re-page after final script lock
Slug lines | 54 | Numerous camera-angle slugs and repeated sets | Grouped into 23 practical environment families
Timeline | 1975–1978 | Wardrobe, vehicles, signage, music and set dressing must remain period-correct | Tiered period depth; no contemporary substitutions in hero frame
Speaking roles | 29 named / featured cues | High day-player casting and fitting load | Role doubling below low tier where story-safe
Central performer | Gary appears in nearly every sequence | Lead fatigue, continuity, prosthetic and school-age casting constraints | 18+ performer below production-company tier
Hospital work | ER, OR, tunnel, recovery, ward, nurses' station, doctors' office | Medical adviser, specialty props, controlled modesty and prosthetics | One redressable medical base below full tier
School work | Exterior, cafeteria, shacks, classrooms, science lab, parking lot | Young-looking cast, period background, controlled public locations | One school / civic-campus base with redresses
Action / safety | Bike jump and crash, embedded axle, seizures, knife chase, fire and wilderness | Stunt coordinator, medic, rigs, mats, fire oversight and insurance | No safety line is removed at any tier
Sensitive material | Teen medical exposure and Sharon/stepfather scene | Closed set, modesty garments, safeguarding and possible intimacy coordinator | Budgeted explicitly; do not rely on camera blocking alone
Wildlife / nature | Deer, fawn, armadillo and birds | Animal handling is costly and schedule-sensitive | Stock/VFX plates below full tier; supervised unit only if approved
Music | The Archies, Pink Floyd and Led Zeppelin cues | Master + publishing can exceed lower-tier means | Replacements below full tier; quote-backed allowance only
Production block | Environments | Key cast | Special requirements | Micro days | Ultra-low days | Low days | Prod. co. days | Lower-tier treatment | Production-company treatment
Bike accident | Dirt track, parking lot, payphone, kitchen | Gary, Will, Mom, kids | Hero/stunt bikes, breakaway wheel, head rig, blood | 1.5 | 2 | 2.5 | 3 | Single controlled exterior cluster; impact sold with inserts | Dedicated rehearsal and insert unit; duplicate rigs
Emergency / first surgery | ER, airport, tunnel, OR | Gary, Mom, doctors, nurses | Open-head prosthetics, medical playback, period hospital | 1.5 | 2 | 2.5 | 3.5 | One medical location repeatedly redressed | Separate OR insert work and fuller hospital dressing
Recovery / prognosis | Recovery, ward, nurses' station | Gary, Mom, Nogan, hospital ensemble | Seizures, catheter/modesty work, wheelchair, jukebox | 1.5 | 2 | 2.5 | 3 | Closed-set inserts and compact ensemble schedule | Safeguarding, specialty inserts and larger medical team
Return to school | K-Mart, school exterior, cafeteria, shacks | Gary, Mom, students, teachers | Orange helmet, period crowds, Pontiac | 1.5 | 2 | 2.5 | 3.5 | One school campus; reduced background | Expanded 1970s crowd and vehicle dressing
Bullying / academics | Parking lot, classrooms, science lab | Gary, Banger, teachers, peers | Retractable knife, run, fall protection, lab props | 1 | 1.5 | 2 | 2.5 | Chase coverage compressed to one block | More geography and background reactions
Friendship / Sharon | Fountain, BBQ, living room | Gary, Sharon, Mike, peers, stepfather | Food, sensitive bedroom/living-room material | 1 | 1 | 1.5 | 1.5 | Controlled modesty and closed set | Intimacy coordinator / safeguarding lead
Withdrawal / future | Park, recruiting offices, wilderness, river | Gary, Mike, recruiters | Campfire, rain, wildlife plates, river safety | 0.5 | 1 | 1 | 1.5 | Accessible park doubles and stock wildlife | Dedicated nature unit if conditions warrant
GED ending | Public library | Gary, librarian, test takers | Period library dress, carts, test packets | 0.5 | 0.5 | 0.5 | 1 | Civic interior redress | Larger practical and background
Sequence-day total (ties to scenario shoot-day assumptions) |  |  |  | 9 | 12 | 15 | 19.5

## Cast & Schedule
Paid Cast & Performer Schedule
Every performer group is paid. Gross wages shown before P&H, payroll fees, overtime, fittings and penalties. Lower tiers cast 18+ performers for teen roles.
Role / group | Script function / tier treatment | Micro count | Days each | Rate/day | Gross | Ultra count | Days each | Rate/day | Gross | Low count | Days each | Rate/day | Gross | Prod count | Days each | Rate/day | Gross
Gary | Lead, age 15–18; 18+ to play younger below production-company tier | 1 | 9 | 400 | 3600 | 1 | 12 | 700 | 8400 | 1 | 15 | 1283 | 19245 | 1 | 20 | 5000 | 100000
Mom | Major supporting role from injury through return to school | 1 | 4 | 300 | 1200 | 1 | 6 | 500 | 3000 | 1 | 8 | 1283 | 10264 | 1 | 10 | 2500 | 25000
Dr. Nogan | Recurring physician / prognosis | 1 | 2 | 257 | 514 | 1 | 3 | 449 | 1347 | 1 | 5 | 1283 | 6415 | 1 | 6 | 2000 | 12000
Dr. Wheeler | Neurosurgeon and operation scenes | 1 | 2 | 257 | 514 | 1 | 2 | 449 | 898 | 1 | 4 | 1283 | 5132 | 1 | 4 | 2200 | 8800
Sharon | Friendship and emotional subplot | 1 | 2 | 257 | 514 | 1 | 3 | 449 | 1347 | 1 | 5 | 1283 | 6415 | 1 | 5 | 2200 | 11000
Mike | Friend across school / park sequences | 1 | 2 | 257 | 514 | 1 | 3 | 449 | 1347 | 1 | 5 | 1283 | 6415 | 1 | 5 | 2000 | 10000
Will | Bike friend and accident witness | 1 | 1 | 257 | 257 | 1 | 1 | 449 | 449 | 1 | 2 | 1283 | 2566 | 1 | 2 | 1600 | 3200
Hospital featured ensemble | Kalus, male nurse, Kim, Kelly, Shawn, aide, orderly, surgical assistant | 6 | 1 | 257 | 1542 | 8 | 1.25 | 449 | 4490 | 8 | 1.5 | 1283 | 15396 | 8 | 2 | 1500 | 24000
School faculty ensemble | Rogers, Sharp, Roche, Richards, Chip and bitter teacher | 4 | 1 | 257 | 1028 | 6 | 1 | 449 | 2694 | 6 | 1.25 | 1283 | 9622.5 | 6 | 1.5 | 1500 | 13500
Teen peers / bullies | Tina, Jeff, Donny, Banger, overweight girl, cafeteria bully and friends | 5 | 1 | 257 | 1285 | 8 | 1 | 449 | 3592 | 8 | 1.25 | 1283 | 12830 | 8 | 1.5 | 1200 | 14400
Recruiters / librarians | Air Force, Navy and two librarian functions; role doubling below low tier | 2 | 1 | 257 | 514 | 3 | 1 | 449 | 1347 | 4 | 1 | 1283 | 5132 | 4 | 1.5 | 1500 | 9000
Sharon's stepfather | Sensitive one-scene supporting role | 1 | 1 | 257 | 257 | 1 | 1 | 449 | 449 | 1 | 1 | 1283 | 1283 | 1 | 1 | 2000 | 2000
Additional day players | Nurses, relatives, students, test takers and clerks | 6 | 1 | 257 | 1542 | 8 | 1 | 449 | 3592 | 10 | 1 | 1283 | 12830 | 10 | 1 | 1283 | 12830
Stunt performers / doubles | Bicycle jump, crash and chase work | 2 | 1 | 257 | 514 | 2 | 2 | 449 | 1796 | 2 | 2 | 1283 | 5132 | 3 | 2 | 1600 | 9600
Background performer-days | School, hospital, airport, cafeteria, K-Mart and library | 50 | 1 | 173 | 8650 | 100 | 1 | 231 | 23100 | 180 | 1 | 231 | 41580 | 300 | 1 | 231 | 69300
Stand-ins / photo doubles | Lead and stunt continuity | 0 | 0 | 0 | 0 | 1 | 8 | 270 | 2160 | 1 | 15 | 270 | 4050 | 2 | 20 | 270 | 10800
Loop group / ADR voices | School, hospital, airport and public spaces | 0 | 0 | 0 | 0 | 8 | 1 | 231 | 1848 | 10 | 1 | 231 | 2310 | 20 | 1 | 231 | 4620
Intimacy / modesty rehearsal performer time | Closed-set rehearsal and choreography allowance | 1 | 1 | 257 | 257 | 1 | 1 | 449 | 449 | 1 | 1 | 1283 | 1283 | 1 | 3 | 1200 | 3600
TOTAL GROSS CAST PAYROLL (before P&H) |  |  |  |  | 22702 |  |  |  | 62305 |  |  |  | 167900.5 |  |  |  | 343650

## Props & Art
Paid Script-Specific Props & Art
Every item is budgeted as a purchase, rental, fabrication, license or consumable. No donated props or free picture vehicles are assumed. General set dressing is separate in each detailed budget.
Prop / art element | Script use | Acquisition | Micro qty | Rate | Total | Ultra qty | Rate | Total | Low qty | Rate | Total | Prod qty | Rate | Total
1970s bicycles — hero and stunt duplicates | Dirt-track jump, commute and crash | Rent / purchase / modify | 2 | 350 | 700 | 3 | 700 | 2100 | 4 | 1200 | 4800 | 5 | 2000 | 10000
Breakaway front wheel, axle and protected head rig | Wheel failure and embedded-axle inserts | Fabricate | 1 | 800 | 800 | 1 | 1800 | 1800 | 1 | 4500 | 4500 | 1 | 12000 | 12000
Dirt ramp, stacked tires and landing dress | Record jump and bike track | Purchase / fabricate | 1 | 300 | 300 | 1 | 900 | 900 | 1 | 2200 | 2200 | 1 | 5000 | 5000
Blood, brain-tissue and wound hand props | Parking lot, ER, surgery and recovery continuity | Fabricate / consumables | 1 | 500 | 500 | 1 | 1400 | 1400 | 1 | 4500 | 4500 | 1 | 18000 | 18000
1970s payphone practical | Collect call to Mom | Rent / fabricate | 1 | 250 | 250 | 1 | 500 | 500 | 1 | 900 | 900 | 1 | 2000 | 2000
Period hospital smalls package | Bandages, razors, urinal, catheter bag, tongue depressors, penlights | Rent / purchase | 1 | 700 | 700 | 1 | 1800 | 1800 | 1 | 4500 | 4500 | 1 | 12000 | 12000
Operating-room surgical insert package | Open-head surgery and awakening | Rent / fabricate | 1 | 500 | 500 | 1 | 1500 | 1500 | 1 | 5000 | 5000 | 1 | 18000 | 18000
Orange motorcycle helmet and continuity doubles | K-Mart purchase and school protection | Purchase / age | 2 | 150 | 300 | 3 | 250 | 750 | 4 | 350 | 1400 | 5 | 500 | 2500
School books, tests, lunch trays and bags | Cafeteria, shacks and classrooms | Purchase / rent | 1 | 400 | 400 | 1 | 1000 | 1000 | 1 | 2500 | 2500 | 1 | 8000 | 8000
Retractable and rubber switchblade set | Banger chase | Purchase | 2 | 75 | 150 | 3 | 125 | 375 | 4 | 225 | 900 | 6 | 200 | 1200
1970s science-lab and overhead-projector package | Atoms and solar-system lessons | Rent / purchase | 1 | 250 | 250 | 1 | 900 | 900 | 1 | 2500 | 2500 | 1 | 8000 | 8000
Jukebox / 45 playback practical | Hospital recreation area | Rent | 1 | 250 | 250 | 1 | 600 | 600 | 1 | 1200 | 1200 | 1 | 4000 | 4000
K-Mart-style retail dress and fictional signage | Helmet purchase | Fabricate / rent | 1 | 300 | 300 | 1 | 1000 | 1000 | 1 | 3000 | 3000 | 1 | 10000 | 10000
Portable 8-track player and cleared-label tape props | Park and wilderness scenes | Purchase / fabricate | 1 | 250 | 250 | 2 | 350 | 700 | 2 | 600 | 1200 | 3 | 400 | 1200
Camping kit, sleeping bag and controlled fire dress | Brazos River camping | Purchase / consumables | 1 | 300 | 300 | 1 | 900 | 900 | 1 | 2200 | 2200 | 1 | 4000 | 4000
Recruiting-office insignia, forms and desk props | Air Force / Navy / Marine offices | Fabricate / rent | 1 | 150 | 150 | 1 | 500 | 500 | 1 | 1200 | 1200 | 1 | 3000 | 3000
GED packets, timer, envelopes and library carts | Fort Worth Public Library ending | Fabricate / rent | 1 | 125 | 125 | 1 | 400 | 400 | 1 | 1000 | 1000 | 1 | 2500 | 2500
1970s Pontiac hero vehicle dressing kit | Arrival at Paschal High School | Rent / picture prep | 1 | 800 | 800 | 1 | 1800 | 1800 | 1 | 3500 | 3500 | 1 | 5000 | 5000
Medical X-rays / PMMA teaching graphics | Skull-plate explanation and doctors' office | Fabricate / license | 1 | 300 | 300 | 1 | 900 | 900 | 1 | 2500 | 2500 | 1 | 5000 | 5000
Airport gate, school and hospital period graphics | T.F. Green, Paschal and medical locations | Print / fabricate | 1 | 250 | 250 | 1 | 800 | 800 | 1 | 2200 | 2200 | 1 | 6000 | 6000
Food, orange juice and practical consumables | Kitchen, cafeteria, BBQ and hospital | Purchase / continuity multiples | 1 | 300 | 300 | 1 | 900 | 900 | 1 | 2500 | 2500 | 1 | 4500 | 4500
Hero prop duplicates, repairs and wear reserve | Continuity across action and period scenes | Allowance | 1 | 700 | 700 | 1 | 2000 | 2000 | 1 | 5000 | 5000 | 1 | 12000 | 12000
TOTAL PAID SCRIPT-SPECIFIC PROPS & ART |  |  |  |  | 8575 |  |  | 23525 |  |  | 59200 |  |  | 153900

## Micro Budget
Micro Budget — Detailed One-Hour TV Budget
Nine-day regional shoot; 18+ actors play teens; hospital is one redressable practical; one school campus; crash is insert-led with stunt supervision; scripted premium songs are replaced. All amounts in USD; planning estimate, not a vendor bid.
Scenario | Micro Budget
Shoot days | 9
Performer / labor framework | SAG-AFTRA Special New Media Category A only if episodic/new-media eligible and total remains under $300,000
Framework ceiling / planning range | 300000
Budget status | WITHIN STATED RANGE
Grand total | 223160.633
Account | Category | Line item | Cost type | Unit | Qty | Rate | Amount | Basis / note
1001 | Development & Above the Line | Life-story rights, releases and chain-of-title reserve | Service | allowance | 1 | 2000 | 2000 | Final rights strategy and participant releases require counsel
1002 | Development & Above the Line | Production rewrite / one-hour polish | Service | allowance | 1 | 2500 | 2500 | Lower tiers need location and speaking-role consolidation
1003 | Development & Above the Line | Producer fees | Crew payroll | flat | 1 | 7000 | 7000 | Financing fees and backend participations excluded
1004 | Development & Above the Line | Director | Crew payroll | flat | 1 | 7500 | 7500 | Full case is an overscale placeholder subject to DGA/signatory terms
1005 | Development & Above the Line | Casting director and sessions | Crew payroll | allowance | 1 | 2000 | 2000 | Includes day-player and young-looking performer search
1006 | Development & Above the Line | Production executive / network delivery supervision | Crew payroll | allowance | 0 | 0 | 0 | Company infrastructure allocation
Development & Above the Line subtotal | [6 empty] | 21000
2001 | Cast | Paid performers per Cast & Schedule | Cast payroll | linked total | 1 |  | 22702 | Gross wages; no deferrals or volunteer acting
Cast subtotal | [6 empty] | 22702
3001 | Production Management | Line producer / UPM | Crew payroll | day | 15 | 350 | 5250 | Prep through wrap; micro combines functions
3002 | Production Management | Production coordinator | Crew payroll | day | 15 | 200 | 3000 | Paid office coordination
3003 | Production Management | 1st assistant director | Crew payroll | day | 10 | 350 | 3500 | Prep, shoot and wrap coverage
3004 | Production Management | 2nd AD / background and minor coordination | Crew payroll | day | 0 | 0 | 0 | Added as crowds and minor work expand
3005 | Production Management | Script supervisor | Crew payroll | day | 9 | 300 | 2700 | Trauma, wardrobe and time-jump continuity
3006 | Production Management | Production assistants | Crew payroll | crew-day | 20 | 150 | 3000 | All PAs paid
3007 | Production Management | Office, printing, radios and communications | Purchase / rental | allowance | 1 | 1500 | 1500 | Production office and set communications
3008 | Production Management | Set medic / first aid | Crew payroll | day | 9 | 300 | 2700 | Present on principal days; dedicated stunt safety below
Production Management subtotal | [6 empty] | 21650
4001 | Camera | Director of photography | Crew payroll | day | 11 | 450 | 4950 | Includes tests and limited prep
4002 | Camera | 1st assistant camera | Crew payroll | day | 9 | 300 | 2700 | Camera focus and builds
4003 | Camera | 2nd AC / DIT / camera utility | Crew payroll | crew-day | 0 | 0 | 0 | Combined roles below low tier
4004 | Camera | Camera, lenses and support package | Rental | shoot day | 9 | 500 | 4500 | Full case includes two bodies and specialty lens support
4005 | Camera | Media, readers, checksum drives and backups | Purchase | allowance | 1 | 1400 | 1400 | At least two verified copies
4006 | Camera | Gimbal, jib, vehicle rig and specialty inserts | Rental | allowance | 1 | 700 | 700 | Bicycle, tunnel and wilderness moves
Camera subtotal | [6 empty] | 14250
5001 | Grip & Electric | Grip and electric crew | Crew payroll | crew-day | 18 | 300 | 5400 | Combined department in lower tiers
5002 | Grip & Electric | Lighting and grip package | Rental | shoot day | 9 | 300 | 2700 | Hospital, night and period-location needs
5003 | Grip & Electric | Generator, distro, fuel and practical power | Rental / purchase | allowance | 1 | 900 | 900 | Remote park and wilderness coverage
Grip & Electric subtotal | [6 empty] | 9000
6001 | Production Sound | Mixer, boom and sound utility | Crew payroll | crew-day | 9 | 350 | 3150 | One-person micro; three-person full team
6002 | Production Sound | Recorder, wireless, timecode and boom package | Rental | shoot day | 9 | 125 | 1125 | Hospital gowns and outdoor coverage require wireless planning
6003 | Production Sound | Playback, earwigs and specialty capture | Rental | allowance | 1 | 400 | 400 | Playback equipment only; music licenses separate
Production Sound subtotal | [6 empty] | 4675
7001 | Art Department & Props | Production designer / art director team | Crew payroll | crew-day | 15 | 300 | 4500 | Design and prep scale with period depth
7002 | Art Department & Props | Set decoration, buyer and dress crew | Crew payroll | crew-day | 15 | 200 | 3000 | Paid construction/dress labor
7003 | Art Department & Props | Prop master and assistants | Crew payroll | crew-day | 9 | 300 | 2700 | Hero prop continuity and stunt-safe duplicates
7004 | Art Department & Props | Paid screenplay props and hero art elements | Linked purchase / rental | linked total | 1 |  | 8575 | Detailed on Props & Art; included exactly once
7005 | Art Department & Props | General period set dressing and expendables | Purchase / rental | allowance | 1 | 1800 | 1800 | Hospital, school, retail, home and office layers
7006 | Art Department & Props | Period graphics, signage and trademark review | Service | allowance | 1 | 700 | 700 | Fictionalize brands where clearance is unavailable
7007 | Art Department & Props | Hospital / school redresses, flats and construction | Fabrication | allowance | 1 | 1200 | 1200 | Multiple scripted hospital and school environments
Art Department & Props subtotal | [6 empty] | 22475
8001 | Wardrobe, Hair & Makeup | Costume design, prep and set wardrobe | Crew payroll | crew-day | 11 | 300 | 3300 | 1975–78 continuity and multiples
8002 | Wardrobe, Hair & Makeup | Period wardrobe rentals, purchases and cleaning | Purchase / rental | allowance | 1 | 1400 | 1400 | Hero, day-player and background wardrobes
8003 | Wardrobe, Hair & Makeup | Hair and makeup crew | Crew payroll | crew-day | 18 | 300 | 5400 | Shaved-head continuity and trauma looks
8004 | Wardrobe, Hair & Makeup | Head wound, surgery and seizure prosthetics | Fabrication / consumable | allowance | 1 | 3000 | 3000 | Tests, appliances, blood and duplicates
8005 | Wardrobe, Hair & Makeup | Wigs, bald cap / shaved-hair effects and materials | Purchase / rental | allowance | 1 | 900 | 900 | Avoid repeated real shaving when continuity demands doubles
8006 | Wardrobe, Hair & Makeup | Intimacy coordinator / modesty garments / closed-set support | Crew payroll / purchase | allowance | 1 | 800 | 800 | For medical exposure and Sharon/stepfather material
Wardrobe, Hair & Makeup subtotal | [6 empty] | 14800
9001 | Locations | Location manager, scouts and assistants | Crew payroll | allowance | 1 | 1500 | 1500 | Scout and contract practical hospital/school alternatives
9002 | Locations | Location fees — hospital, school, retail, home and library | Location | allowance | 1 | 4000 | 4000 | No donated facilities assumed
9003 | Locations | Permits, parking, police, fire and public-safety support | Permit / service | allowance | 1 | 900 | 900 | Bike work, payphone/store, park and controlled fire
9004 | Locations | Cleanup, restoration, security and site protection | Service | allowance | 1 | 900 | 900 | Schools, hospitals and public interiors
9005 | Locations | Wilderness / river access and fire oversight | Location / service | allowance | 1 | 800 | 800 | Wildlife work remains contingent on approved plan
Locations subtotal | [6 empty] | 8100
10001 | Transportation & Travel | Transportation coordinator, captain and drivers | Crew payroll | allowance | 1 | 1800 | 1800 | Paid drivers and coordination
10002 | Transportation & Travel | Production vans, box truck and passenger vehicles | Rental | allowance | 1 | 2800 | 2800 | Scaled vehicle package
10003 | Transportation & Travel | Picture vehicles — Pontiac and period traffic | Rental | allowance | 1 | 1400 | 1400 | Hero vehicle prep is detailed in Props & Art; this covers operating rentals/traffic
10004 | Transportation & Travel | Fuel, mileage, tolls and parking | Purchase | allowance | 1 | 1400 | 1400 | Texas regional base
10005 | Transportation & Travel | Cast/crew lodging, airfare and per diem | Travel | allowance | 1 | 900 | 900 | Lower tiers rely on local hires; no unpaid lodging assumed
Transportation & Travel subtotal | [6 empty] | 8300
11001 | Stunts, Medical Effects & Safety | Stunt coordinator | Crew payroll | day | 3 | 1283 | 3849 | Current full coordinator reference retained even in reduced performer tiers
11002 | Stunts, Medical Effects & Safety | Bicycle rigs, mats, rehearsal space and safety equipment | Rental / fabrication | allowance | 1 | 2300 | 2300 | Protected jump, wheel failure and crash design
11003 | Stunts, Medical Effects & Safety | Knife choreography and stunt-safe weapon handling | Crew payroll / purchase | allowance | 1 | 500 | 500 | No sharp weapon used for contact work
11004 | Stunts, Medical Effects & Safety | Fire safety, rain / wet-weather and wilderness safety | Service | allowance | 1 | 500 | 500 | Campfire and exterior unit
11005 | Stunts, Medical Effects & Safety | Medical adviser and procedure review | Service | allowance | 1 | 1000 | 1000 | ER, surgery, seizure and recovery detail
11006 | Stunts, Medical Effects & Safety | Studio teacher / welfare worker / child labor coordinator | Crew payroll | allowance | 0 | 0 | 0 | Required scope depends on age-authentic minor casting and jurisdiction
Stunts, Medical Effects & Safety subtotal | [6 empty] | 8149
12001 | Visual Effects | VFX supervision, tests and turnover | Service | allowance | 1 | 400 | 400 | Plan crash and medical shots before photography
12002 | Visual Effects | Head injury, surgery and blood cleanup / enhancement | Service | allowance | 1 | 1800 | 1800 | Complements practical prosthetics
12003 | Visual Effects | Double vision, period cleanup and environment fixes | Service | allowance | 1 | 1200 | 1200 | POV work and removal of modern intrusions
12004 | Visual Effects | Wildlife / nature plates and comps | Service / license | allowance | 1 | 400 | 400 | Avoids unsupervised wildlife staging
Visual Effects subtotal | [6 empty] | 3800
13001 | Post-Production | Picture editor | Crew payroll | day | 40 | 250 | 10000 | One-hour narrative editorial
13002 | Post-Production | Assistant editor / post coordinator | Crew payroll | day | 0 | 0 | 0 | Combined with editor in micro case
13003 | Post-Production | Edit systems, storage, review and archive | Rental / purchase | allowance | 1 | 1400 | 1400 | Separate from camera originals
13004 | Post-Production | Sound editorial, Foley and design | Service | allowance | 1 | 3800 | 3800 | Brain-squish POV, hospital, bikes, wilderness and crowds
13005 | Post-Production | ADR, loop group and voice processing | Service | allowance | 1 | 700 | 700 | Gibberish/POV and public-space repairs
13006 | Post-Production | Final mix and M&E | Service | allowance | 1 | 1800 | 1800 | M&E for international delivery
13007 | Post-Production | Color grade and finishing | Service | allowance | 1 | 1800 | 1800 | Period look and medical continuity
13008 | Post-Production | Online, conform and mastering | Service | allowance | 1 | 1600 | 1600 | Broadcast/streaming masters
13009 | Post-Production | QC, captions, audio description and deliverables | Service | allowance | 1 | 700 | 700 | Accessibility and distributor deliverables
13010 | Post-Production | Archival / stock footage and wildlife licenses | License | allowance | 1 | 400 | 400 | Quote required; no unlicensed use
Post-Production subtotal | [6 empty] | 22200
14001 | Music | Music supervisor / clearance administration | Service | allowance | 1 | 500 | 500 | Begin before scripted playback
14002 | Music | Composer fee | Service | allowance | 1 | 1800 | 1800 | Original score
14003 | Music | Score recording, musicians, studio and mix | Service | allowance | 1 | 400 | 400 | Mostly in-the-box below full tier
14004 | Music | Source-song master and publishing licenses | License | allowance | 1 | 0 | 0 | Premium catalog cues require separate master and publishing quotes; zero means replacement
14005 | Music | Cue sheets, music legal and license delivery | Service | allowance | 1 | 300 | 300 | Required delivery paperwork
Music subtotal | [6 empty] | 3000
15001 | Insurance, Legal, Admin & Delivery | Production package insurance | Insurance | allowance | 1 | 5000 | 5000 | GL, equipment, auto and specialty-risk allowances
15002 | Insurance, Legal, Admin & Delivery | Production legal, contracts and clearances | Service | allowance | 1 | 2200 | 2200 | Rights, brands, sensitive material and releases
15003 | Insurance, Legal, Admin & Delivery | Production accounting and cost reporting | Service | allowance | 1 | 1400 | 1400 | Cost reports and tax filings
15004 | Insurance, Legal, Admin & Delivery | Errors & omissions insurance | Insurance | allowance | 1 | 2500 | 2500 | Common distributor requirement
15005 | Insurance, Legal, Admin & Delivery | Publicity stills, EPK and delivery incidentals | Service | allowance | 1 | 900 | 900 | Distribution marketing spend excluded
15006 | Insurance, Legal, Admin & Delivery | Production-company overhead | Overhead | allowance | 0 | 0 | 0 | Corporate infrastructure allocation; financing costs excluded
Insurance, Legal, Admin & Delivery subtotal | [6 empty] | 12000
Subtotal before payroll burdens and contingency | [6 empty] | 196101
Cast pension & health | [6 empty] | 4880.93
Crew payroll taxes / workers compensation / benefits burden | [6 empty] | 9778.89
Payroll company fee | [6 empty] | 2790.025
Subtotal before completion bond and contingency | [6 empty] | 213550.845
Completion bond | [6 empty] | 0
Contingency reserve | [6 empty] | 9609.788
GRAND TOTAL | [6 empty] | 223160.633

## Ultra-Low Budget
Ultra-Low Budget — Detailed One-Hour TV Budget
Twelve-day independent shoot; controlled bicycle stunt day; fuller hospital coverage; limited period background; combined departments; library/original music with a small source allowance. All amounts in USD; planning estimate, not a vendor bid.
Scenario | Ultra-Low Budget
Shoot days | 12
Performer / labor framework | SAG-AFTRA Special New Media Category B only if episodic/new-media eligible and total remains under $700,000
Framework ceiling / planning range | 700000
Budget status | WITHIN STATED RANGE
Grand total | 600218.8237
Account | Category | Line item | Cost type | Unit | Qty | Rate | Amount | Basis / note
1001 | Development & Above the Line | Life-story rights, releases and chain-of-title reserve | Service | allowance | 1 | 5000 | 5000 | Final rights strategy and participant releases require counsel
1002 | Development & Above the Line | Production rewrite / one-hour polish | Service | allowance | 1 | 7000 | 7000 | Lower tiers need location and speaking-role consolidation
1003 | Development & Above the Line | Producer fees | Crew payroll | flat | 1 | 20000 | 20000 | Financing fees and backend participations excluded
1004 | Development & Above the Line | Director | Crew payroll | flat | 1 | 20000 | 20000 | Full case is an overscale placeholder subject to DGA/signatory terms
1005 | Development & Above the Line | Casting director and sessions | Crew payroll | allowance | 1 | 5000 | 5000 | Includes day-player and young-looking performer search
1006 | Development & Above the Line | Production executive / network delivery supervision | Crew payroll | allowance | 0 | 0 | 0 | Company infrastructure allocation
Development & Above the Line subtotal | [6 empty] | 57000
2001 | Cast | Paid performers per Cast & Schedule | Cast payroll | linked total | 1 |  | 62305 | Gross wages; no deferrals or volunteer acting
Cast subtotal | [6 empty] | 62305
3001 | Production Management | Line producer / UPM | Crew payroll | day | 25 | 525 | 13125 | Prep through wrap; micro combines functions
3002 | Production Management | Production coordinator | Crew payroll | day | 25 | 325 | 8125 | Paid office coordination
3003 | Production Management | 1st assistant director | Crew payroll | day | 15 | 525 | 7875 | Prep, shoot and wrap coverage
3004 | Production Management | 2nd AD / background and minor coordination | Crew payroll | day | 10 | 350 | 3500 | Added as crowds and minor work expand
3005 | Production Management | Script supervisor | Crew payroll | day | 12 | 425 | 5100 | Trauma, wardrobe and time-jump continuity
3006 | Production Management | Production assistants | Crew payroll | crew-day | 48 | 190 | 9120 | All PAs paid
3007 | Production Management | Office, printing, radios and communications | Purchase / rental | allowance | 1 | 3500 | 3500 | Production office and set communications
3008 | Production Management | Set medic / first aid | Crew payroll | day | 12 | 400 | 4800 | Present on principal days; dedicated stunt safety below
Production Management subtotal | [6 empty] | 55145
4001 | Camera | Director of photography | Crew payroll | day | 17 | 700 | 11900 | Includes tests and limited prep
4002 | Camera | 1st assistant camera | Crew payroll | day | 12 | 425 | 5100 | Camera focus and builds
4003 | Camera | 2nd AC / DIT / camera utility | Crew payroll | crew-day | 12 | 300 | 3600 | Combined roles below low tier
4004 | Camera | Camera, lenses and support package | Rental | shoot day | 12 | 1150 | 13800 | Full case includes two bodies and specialty lens support
4005 | Camera | Media, readers, checksum drives and backups | Purchase | allowance | 1 | 3000 | 3000 | At least two verified copies
4006 | Camera | Gimbal, jib, vehicle rig and specialty inserts | Rental | allowance | 1 | 2500 | 2500 | Bicycle, tunnel and wilderness moves
Camera subtotal | [6 empty] | 39900
5001 | Grip & Electric | Grip and electric crew | Crew payroll | crew-day | 45 | 375 | 16875 | Combined department in lower tiers
5002 | Grip & Electric | Lighting and grip package | Rental | shoot day | 12 | 600 | 7200 | Hospital, night and period-location needs
5003 | Grip & Electric | Generator, distro, fuel and practical power | Rental / purchase | allowance | 1 | 2200 | 2200 | Remote park and wilderness coverage
Grip & Electric subtotal | [6 empty] | 26275
6001 | Production Sound | Mixer, boom and sound utility | Crew payroll | crew-day | 24 | 350 | 8400 | One-person micro; three-person full team
6002 | Production Sound | Recorder, wireless, timecode and boom package | Rental | shoot day | 12 | 275 | 3300 | Hospital gowns and outdoor coverage require wireless planning
6003 | Production Sound | Playback, earwigs and specialty capture | Rental | allowance | 1 | 900 | 900 | Playback equipment only; music licenses separate
Production Sound subtotal | [6 empty] | 12600
7001 | Art Department & Props | Production designer / art director team | Crew payroll | crew-day | 35 | 375 | 13125 | Design and prep scale with period depth
7002 | Art Department & Props | Set decoration, buyer and dress crew | Crew payroll | crew-day | 36 | 275 | 9900 | Paid construction/dress labor
7003 | Art Department & Props | Prop master and assistants | Crew payroll | crew-day | 12 | 425 | 5100 | Hero prop continuity and stunt-safe duplicates
7004 | Art Department & Props | Paid screenplay props and hero art elements | Linked purchase / rental | linked total | 1 |  | 23525 | Detailed on Props & Art; included exactly once
7005 | Art Department & Props | General period set dressing and expendables | Purchase / rental | allowance | 1 | 5000 | 5000 | Hospital, school, retail, home and office layers
7006 | Art Department & Props | Period graphics, signage and trademark review | Service | allowance | 1 | 1800 | 1800 | Fictionalize brands where clearance is unavailable
7007 | Art Department & Props | Hospital / school redresses, flats and construction | Fabrication | allowance | 1 | 4000 | 4000 | Multiple scripted hospital and school environments
Art Department & Props subtotal | [6 empty] | 62450
8001 | Wardrobe, Hair & Makeup | Costume design, prep and set wardrobe | Crew payroll | crew-day | 24 | 350 | 8400 | 1975–78 continuity and multiples
8002 | Wardrobe, Hair & Makeup | Period wardrobe rentals, purchases and cleaning | Purchase / rental | allowance | 1 | 4500 | 4500 | Hero, day-player and background wardrobes
8003 | Wardrobe, Hair & Makeup | Hair and makeup crew | Crew payroll | crew-day | 34 | 350 | 11900 | Shaved-head continuity and trauma looks
8004 | Wardrobe, Hair & Makeup | Head wound, surgery and seizure prosthetics | Fabrication / consumable | allowance | 1 | 7500 | 7500 | Tests, appliances, blood and duplicates
8005 | Wardrobe, Hair & Makeup | Wigs, bald cap / shaved-hair effects and materials | Purchase / rental | allowance | 1 | 2500 | 2500 | Avoid repeated real shaving when continuity demands doubles
8006 | Wardrobe, Hair & Makeup | Intimacy coordinator / modesty garments / closed-set support | Crew payroll / purchase | allowance | 1 | 1600 | 1600 | For medical exposure and Sharon/stepfather material
Wardrobe, Hair & Makeup subtotal | [6 empty] | 36400
9001 | Locations | Location manager, scouts and assistants | Crew payroll | allowance | 1 | 4500 | 4500 | Scout and contract practical hospital/school alternatives
9002 | Locations | Location fees — hospital, school, retail, home and library | Location | allowance | 1 | 10000 | 10000 | No donated facilities assumed
9003 | Locations | Permits, parking, police, fire and public-safety support | Permit / service | allowance | 1 | 2500 | 2500 | Bike work, payphone/store, park and controlled fire
9004 | Locations | Cleanup, restoration, security and site protection | Service | allowance | 1 | 2500 | 2500 | Schools, hospitals and public interiors
9005 | Locations | Wilderness / river access and fire oversight | Location / service | allowance | 1 | 2500 | 2500 | Wildlife work remains contingent on approved plan
Locations subtotal | [6 empty] | 22000
10001 | Transportation & Travel | Transportation coordinator, captain and drivers | Crew payroll | allowance | 1 | 6000 | 6000 | Paid drivers and coordination
10002 | Transportation & Travel | Production vans, box truck and passenger vehicles | Rental | allowance | 1 | 7000 | 7000 | Scaled vehicle package
10003 | Transportation & Travel | Picture vehicles — Pontiac and period traffic | Rental | allowance | 1 | 4500 | 4500 | Hero vehicle prep is detailed in Props & Art; this covers operating rentals/traffic
10004 | Transportation & Travel | Fuel, mileage, tolls and parking | Purchase | allowance | 1 | 3000 | 3000 | Texas regional base
10005 | Transportation & Travel | Cast/crew lodging, airfare and per diem | Travel | allowance | 1 | 3500 | 3500 | Lower tiers rely on local hires; no unpaid lodging assumed
Transportation & Travel subtotal | [6 empty] | 24000
11001 | Stunts, Medical Effects & Safety | Stunt coordinator | Crew payroll | day | 5 | 1283 | 6415 | Current full coordinator reference retained even in reduced performer tiers
11002 | Stunts, Medical Effects & Safety | Bicycle rigs, mats, rehearsal space and safety equipment | Rental / fabrication | allowance | 1 | 6000 | 6000 | Protected jump, wheel failure and crash design
11003 | Stunts, Medical Effects & Safety | Knife choreography and stunt-safe weapon handling | Crew payroll / purchase | allowance | 1 | 1200 | 1200 | No sharp weapon used for contact work
11004 | Stunts, Medical Effects & Safety | Fire safety, rain / wet-weather and wilderness safety | Service | allowance | 1 | 1200 | 1200 | Campfire and exterior unit
11005 | Stunts, Medical Effects & Safety | Medical adviser and procedure review | Service | allowance | 1 | 2500 | 2500 | ER, surgery, seizure and recovery detail
11006 | Stunts, Medical Effects & Safety | Studio teacher / welfare worker / child labor coordinator | Crew payroll | allowance | 0 | 0 | 0 | Required scope depends on age-authentic minor casting and jurisdiction
Stunts, Medical Effects & Safety subtotal | [6 empty] | 17315
12001 | Visual Effects | VFX supervision, tests and turnover | Service | allowance | 1 | 1500 | 1500 | Plan crash and medical shots before photography
12002 | Visual Effects | Head injury, surgery and blood cleanup / enhancement | Service | allowance | 1 | 5000 | 5000 | Complements practical prosthetics
12003 | Visual Effects | Double vision, period cleanup and environment fixes | Service | allowance | 1 | 4000 | 4000 | POV work and removal of modern intrusions
12004 | Visual Effects | Wildlife / nature plates and comps | Service / license | allowance | 1 | 1200 | 1200 | Avoids unsupervised wildlife staging
Visual Effects subtotal | [6 empty] | 11700
13001 | Post-Production | Picture editor | Crew payroll | day | 55 | 375 | 20625 | One-hour narrative editorial
13002 | Post-Production | Assistant editor / post coordinator | Crew payroll | day | 15 | 250 | 3750 | Combined with editor in micro case
13003 | Post-Production | Edit systems, storage, review and archive | Rental / purchase | allowance | 1 | 3500 | 3500 | Separate from camera originals
13004 | Post-Production | Sound editorial, Foley and design | Service | allowance | 1 | 10000 | 10000 | Brain-squish POV, hospital, bikes, wilderness and crowds
13005 | Post-Production | ADR, loop group and voice processing | Service | allowance | 1 | 1800 | 1800 | Gibberish/POV and public-space repairs
13006 | Post-Production | Final mix and M&E | Service | allowance | 1 | 4500 | 4500 | M&E for international delivery
13007 | Post-Production | Color grade and finishing | Service | allowance | 1 | 4500 | 4500 | Period look and medical continuity
13008 | Post-Production | Online, conform and mastering | Service | allowance | 1 | 4000 | 4000 | Broadcast/streaming masters
13009 | Post-Production | QC, captions, audio description and deliverables | Service | allowance | 1 | 1800 | 1800 | Accessibility and distributor deliverables
13010 | Post-Production | Archival / stock footage and wildlife licenses | License | allowance | 1 | 1500 | 1500 | Quote required; no unlicensed use
Post-Production subtotal | [6 empty] | 55975
14001 | Music | Music supervisor / clearance administration | Service | allowance | 1 | 1400 | 1400 | Begin before scripted playback
14002 | Music | Composer fee | Service | allowance | 1 | 4500 | 4500 | Original score
14003 | Music | Score recording, musicians, studio and mix | Service | allowance | 1 | 1200 | 1200 | Mostly in-the-box below full tier
14004 | Music | Source-song master and publishing licenses | License | allowance | 1 | 1000 | 1000 | Premium catalog cues require separate master and publishing quotes; zero means replacement
14005 | Music | Cue sheets, music legal and license delivery | Service | allowance | 1 | 700 | 700 | Required delivery paperwork
Music subtotal | [6 empty] | 8800
15001 | Insurance, Legal, Admin & Delivery | Production package insurance | Insurance | allowance | 1 | 11000 | 11000 | GL, equipment, auto and specialty-risk allowances
15002 | Insurance, Legal, Admin & Delivery | Production legal, contracts and clearances | Service | allowance | 1 | 5000 | 5000 | Rights, brands, sensitive material and releases
15003 | Insurance, Legal, Admin & Delivery | Production accounting and cost reporting | Service | allowance | 1 | 3500 | 3500 | Cost reports and tax filings
15004 | Insurance, Legal, Admin & Delivery | Errors & omissions insurance | Insurance | allowance | 1 | 4500 | 4500 | Common distributor requirement
15005 | Insurance, Legal, Admin & Delivery | Publicity stills, EPK and delivery incidentals | Service | allowance | 1 | 2500 | 2500 | Distribution marketing spend excluded
15006 | Insurance, Legal, Admin & Delivery | Production-company overhead | Overhead | allowance | 0 | 0 | 0 | Corporate infrastructure allocation; financing costs excluded
Insurance, Legal, Admin & Delivery subtotal | [6 empty] | 26500
Subtotal before payroll burdens and contingency | [6 empty] | 518365
Cast pension & health | [6 empty] | 13395.575
Crew payroll taxes / workers compensation / benefits burden | [6 empty] | 32512.9
Payroll company fee | [6 empty] | 7363.5
Subtotal before completion bond and contingency | [6 empty] | 571636.975
Completion bond | [6 empty] | 0
Contingency reserve | [6 empty] | 28581.8488
GRAND TOTAL | [6 empty] | 600218.8237

## Low Budget
Low Budget — Detailed One-Hour TV Budget
Fifteen-day low-budget television execution; union-scale cast; dedicated art, wardrobe and prosthetics; more period vehicles/background; original score and quoted selective source music. All amounts in USD; planning estimate, not a vendor bid.
Scenario | Low Budget
Shoot days | 15
Performer / labor framework | Full 2026 SAG-AFTRA Television rates assumed because this case is expected to exceed the $1,000,000 Special New Media ceiling
Framework ceiling / planning range | 2000000
Budget status | WITHIN STATED RANGE
Grand total | 1450727.6986
Account | Category | Line item | Cost type | Unit | Qty | Rate | Amount | Basis / note
1001 | Development & Above the Line | Life-story rights, releases and chain-of-title reserve | Service | allowance | 1 | 10000 | 10000 | Final rights strategy and participant releases require counsel
1002 | Development & Above the Line | Production rewrite / one-hour polish | Service | allowance | 1 | 15000 | 15000 | Lower tiers need location and speaking-role consolidation
1003 | Development & Above the Line | Producer fees | Crew payroll | flat | 1 | 35000 | 35000 | Financing fees and backend participations excluded
1004 | Development & Above the Line | Director | Crew payroll | flat | 1 | 35000 | 35000 | Full case is an overscale placeholder subject to DGA/signatory terms
1005 | Development & Above the Line | Casting director and sessions | Crew payroll | allowance | 1 | 10000 | 10000 | Includes day-player and young-looking performer search
1006 | Development & Above the Line | Production executive / network delivery supervision | Crew payroll | allowance | 1 | 5000 | 5000 | Company infrastructure allocation
Development & Above the Line subtotal | [6 empty] | 110000
2001 | Cast | Paid performers per Cast & Schedule | Cast payroll | linked total | 1 |  | 167900.5 | Gross wages; no deferrals or volunteer acting
Cast subtotal | [6 empty] | 167900.5
3001 | Production Management | Line producer / UPM | Crew payroll | day | 35 | 800 | 28000 | Prep through wrap; micro combines functions
3002 | Production Management | Production coordinator | Crew payroll | day | 35 | 525 | 18375 | Paid office coordination
3003 | Production Management | 1st assistant director | Crew payroll | day | 20 | 800 | 16000 | Prep, shoot and wrap coverage
3004 | Production Management | 2nd AD / background and minor coordination | Crew payroll | day | 15 | 600 | 9000 | Added as crowds and minor work expand
3005 | Production Management | Script supervisor | Crew payroll | day | 15 | 625 | 9375 | Trauma, wardrobe and time-jump continuity
3006 | Production Management | Production assistants | Crew payroll | crew-day | 80 | 240 | 19200 | All PAs paid
3007 | Production Management | Office, printing, radios and communications | Purchase / rental | allowance | 1 | 7000 | 7000 | Production office and set communications
3008 | Production Management | Set medic / first aid | Crew payroll | day | 15 | 575 | 8625 | Present on principal days; dedicated stunt safety below
Production Management subtotal | [6 empty] | 115575
4001 | Camera | Director of photography | Crew payroll | day | 23 | 1100 | 25300 | Includes tests and limited prep
4002 | Camera | 1st assistant camera | Crew payroll | day | 15 | 650 | 9750 | Camera focus and builds
4003 | Camera | 2nd AC / DIT / camera utility | Crew payroll | crew-day | 25 | 475 | 11875 | Combined roles below low tier
4004 | Camera | Camera, lenses and support package | Rental | shoot day | 15 | 2200 | 33000 | Full case includes two bodies and specialty lens support
4005 | Camera | Media, readers, checksum drives and backups | Purchase | allowance | 1 | 6500 | 6500 | At least two verified copies
4006 | Camera | Gimbal, jib, vehicle rig and specialty inserts | Rental | allowance | 1 | 6500 | 6500 | Bicycle, tunnel and wilderness moves
Camera subtotal | [6 empty] | 92925
5001 | Grip & Electric | Grip and electric crew | Crew payroll | crew-day | 75 | 550 | 41250 | Combined department in lower tiers
5002 | Grip & Electric | Lighting and grip package | Rental | shoot day | 15 | 1100 | 16500 | Hospital, night and period-location needs
5003 | Grip & Electric | Generator, distro, fuel and practical power | Rental / purchase | allowance | 1 | 4500 | 4500 | Remote park and wilderness coverage
Grip & Electric subtotal | [6 empty] | 62250
6001 | Production Sound | Mixer, boom and sound utility | Crew payroll | crew-day | 40 | 525 | 21000 | One-person micro; three-person full team
6002 | Production Sound | Recorder, wireless, timecode and boom package | Rental | shoot day | 15 | 550 | 8250 | Hospital gowns and outdoor coverage require wireless planning
6003 | Production Sound | Playback, earwigs and specialty capture | Rental | allowance | 1 | 2200 | 2200 | Playback equipment only; music licenses separate
Production Sound subtotal | [6 empty] | 31450
7001 | Art Department & Props | Production designer / art director team | Crew payroll | crew-day | 55 | 600 | 33000 | Design and prep scale with period depth
7002 | Art Department & Props | Set decoration, buyer and dress crew | Crew payroll | crew-day | 65 | 425 | 27625 | Paid construction/dress labor
7003 | Art Department & Props | Prop master and assistants | Crew payroll | crew-day | 15 | 700 | 10500 | Hero prop continuity and stunt-safe duplicates
7004 | Art Department & Props | Paid screenplay props and hero art elements | Linked purchase / rental | linked total | 1 |  | 59200 | Detailed on Props & Art; included exactly once
7005 | Art Department & Props | General period set dressing and expendables | Purchase / rental | allowance | 1 | 12000 | 12000 | Hospital, school, retail, home and office layers
7006 | Art Department & Props | Period graphics, signage and trademark review | Service | allowance | 1 | 4500 | 4500 | Fictionalize brands where clearance is unavailable
7007 | Art Department & Props | Hospital / school redresses, flats and construction | Fabrication | allowance | 1 | 12000 | 12000 | Multiple scripted hospital and school environments
Art Department & Props subtotal | [6 empty] | 158825
8001 | Wardrobe, Hair & Makeup | Costume design, prep and set wardrobe | Crew payroll | crew-day | 40 | 550 | 22000 | 1975–78 continuity and multiples
8002 | Wardrobe, Hair & Makeup | Period wardrobe rentals, purchases and cleaning | Purchase / rental | allowance | 1 | 12000 | 12000 | Hero, day-player and background wardrobes
8003 | Wardrobe, Hair & Makeup | Hair and makeup crew | Crew payroll | crew-day | 55 | 550 | 30250 | Shaved-head continuity and trauma looks
8004 | Wardrobe, Hair & Makeup | Head wound, surgery and seizure prosthetics | Fabrication / consumable | allowance | 1 | 18000 | 18000 | Tests, appliances, blood and duplicates
8005 | Wardrobe, Hair & Makeup | Wigs, bald cap / shaved-hair effects and materials | Purchase / rental | allowance | 1 | 6500 | 6500 | Avoid repeated real shaving when continuity demands doubles
8006 | Wardrobe, Hair & Makeup | Intimacy coordinator / modesty garments / closed-set support | Crew payroll / purchase | allowance | 1 | 3500 | 3500 | For medical exposure and Sharon/stepfather material
Wardrobe, Hair & Makeup subtotal | [6 empty] | 92250
9001 | Locations | Location manager, scouts and assistants | Crew payroll | allowance | 1 | 10000 | 10000 | Scout and contract practical hospital/school alternatives
9002 | Locations | Location fees — hospital, school, retail, home and library | Location | allowance | 1 | 22000 | 22000 | No donated facilities assumed
9003 | Locations | Permits, parking, police, fire and public-safety support | Permit / service | allowance | 1 | 6000 | 6000 | Bike work, payphone/store, park and controlled fire
9004 | Locations | Cleanup, restoration, security and site protection | Service | allowance | 1 | 6000 | 6000 | Schools, hospitals and public interiors
9005 | Locations | Wilderness / river access and fire oversight | Location / service | allowance | 1 | 5000 | 5000 | Wildlife work remains contingent on approved plan
Locations subtotal | [6 empty] | 49000
10001 | Transportation & Travel | Transportation coordinator, captain and drivers | Crew payroll | allowance | 1 | 15000 | 15000 | Paid drivers and coordination
10002 | Transportation & Travel | Production vans, box truck and passenger vehicles | Rental | allowance | 1 | 13000 | 13000 | Scaled vehicle package
10003 | Transportation & Travel | Picture vehicles — Pontiac and period traffic | Rental | allowance | 1 | 10000 | 10000 | Hero vehicle prep is detailed in Props & Art; this covers operating rentals/traffic
10004 | Transportation & Travel | Fuel, mileage, tolls and parking | Purchase | allowance | 1 | 6000 | 6000 | Texas regional base
10005 | Transportation & Travel | Cast/crew lodging, airfare and per diem | Travel | allowance | 1 | 9000 | 9000 | Lower tiers rely on local hires; no unpaid lodging assumed
Transportation & Travel subtotal | [6 empty] | 53000
11001 | Stunts, Medical Effects & Safety | Stunt coordinator | Crew payroll | day | 7 | 1283 | 8981 | Current full coordinator reference retained even in reduced performer tiers
11002 | Stunts, Medical Effects & Safety | Bicycle rigs, mats, rehearsal space and safety equipment | Rental / fabrication | allowance | 1 | 12000 | 12000 | Protected jump, wheel failure and crash design
11003 | Stunts, Medical Effects & Safety | Knife choreography and stunt-safe weapon handling | Crew payroll / purchase | allowance | 1 | 2500 | 2500 | No sharp weapon used for contact work
11004 | Stunts, Medical Effects & Safety | Fire safety, rain / wet-weather and wilderness safety | Service | allowance | 1 | 2500 | 2500 | Campfire and exterior unit
11005 | Stunts, Medical Effects & Safety | Medical adviser and procedure review | Service | allowance | 1 | 5000 | 5000 | ER, surgery, seizure and recovery detail
11006 | Stunts, Medical Effects & Safety | Studio teacher / welfare worker / child labor coordinator | Crew payroll | allowance | 1 | 4000 | 4000 | Required scope depends on age-authentic minor casting and jurisdiction
Stunts, Medical Effects & Safety subtotal | [6 empty] | 34981
12001 | Visual Effects | VFX supervision, tests and turnover | Service | allowance | 1 | 4000 | 4000 | Plan crash and medical shots before photography
12002 | Visual Effects | Head injury, surgery and blood cleanup / enhancement | Service | allowance | 1 | 12000 | 12000 | Complements practical prosthetics
12003 | Visual Effects | Double vision, period cleanup and environment fixes | Service | allowance | 1 | 9000 | 9000 | POV work and removal of modern intrusions
12004 | Visual Effects | Wildlife / nature plates and comps | Service / license | allowance | 1 | 3000 | 3000 | Avoids unsupervised wildlife staging
Visual Effects subtotal | [6 empty] | 28000
13001 | Post-Production | Picture editor | Crew payroll | day | 75 | 600 | 45000 | One-hour narrative editorial
13002 | Post-Production | Assistant editor / post coordinator | Crew payroll | day | 35 | 375 | 13125 | Combined with editor in micro case
13003 | Post-Production | Edit systems, storage, review and archive | Rental / purchase | allowance | 1 | 7000 | 7000 | Separate from camera originals
13004 | Post-Production | Sound editorial, Foley and design | Service | allowance | 1 | 22000 | 22000 | Brain-squish POV, hospital, bikes, wilderness and crowds
13005 | Post-Production | ADR, loop group and voice processing | Service | allowance | 1 | 4500 | 4500 | Gibberish/POV and public-space repairs
13006 | Post-Production | Final mix and M&E | Service | allowance | 1 | 10000 | 10000 | M&E for international delivery
13007 | Post-Production | Color grade and finishing | Service | allowance | 1 | 10000 | 10000 | Period look and medical continuity
13008 | Post-Production | Online, conform and mastering | Service | allowance | 1 | 9000 | 9000 | Broadcast/streaming masters
13009 | Post-Production | QC, captions, audio description and deliverables | Service | allowance | 1 | 4500 | 4500 | Accessibility and distributor deliverables
13010 | Post-Production | Archival / stock footage and wildlife licenses | License | allowance | 1 | 4500 | 4500 | Quote required; no unlicensed use
Post-Production subtotal | [6 empty] | 129625
14001 | Music | Music supervisor / clearance administration | Service | allowance | 1 | 3500 | 3500 | Begin before scripted playback
14002 | Music | Composer fee | Service | allowance | 1 | 10000 | 10000 | Original score
14003 | Music | Score recording, musicians, studio and mix | Service | allowance | 1 | 3500 | 3500 | Mostly in-the-box below full tier
14004 | Music | Source-song master and publishing licenses | License | allowance | 1 | 5000 | 5000 | Premium catalog cues require separate master and publishing quotes; zero means replacement
14005 | Music | Cue sheets, music legal and license delivery | Service | allowance | 1 | 1600 | 1600 | Required delivery paperwork
Music subtotal | [6 empty] | 23600
15001 | Insurance, Legal, Admin & Delivery | Production package insurance | Insurance | allowance | 1 | 22000 | 22000 | GL, equipment, auto and specialty-risk allowances
15002 | Insurance, Legal, Admin & Delivery | Production legal, contracts and clearances | Service | allowance | 1 | 10000 | 10000 | Rights, brands, sensitive material and releases
15003 | Insurance, Legal, Admin & Delivery | Production accounting and cost reporting | Service | allowance | 1 | 7000 | 7000 | Cost reports and tax filings
15004 | Insurance, Legal, Admin & Delivery | Errors & omissions insurance | Insurance | allowance | 1 | 7000 | 7000 | Common distributor requirement
15005 | Insurance, Legal, Admin & Delivery | Publicity stills, EPK and delivery incidentals | Service | allowance | 1 | 6000 | 6000 | Distribution marketing spend excluded
15006 | Insurance, Legal, Admin & Delivery | Production-company overhead | Overhead | allowance | 1 | 10000 | 10000 | Corporate infrastructure allocation; financing costs excluded
Insurance, Legal, Admin & Delivery subtotal | [6 empty] | 62000
Subtotal before payroll burdens and contingency | [6 empty] | 1211381.5
Cast pension & health | [6 empty] | 36098.6075
Crew payroll taxes / workers compensation / benefits burden | [6 empty] | 94001.58
Payroll company fee | [6 empty] | 20703.945
Subtotal before completion bond and contingency | [6 empty] | 1362185.6325
Completion bond | [6 empty] | 0
Contingency reserve | [6 empty] | 88542.0661
GRAND TOTAL | [6 empty] | 1450727.6986

## Production Co
Production Company — Detailed One-Hour TV Budget
Twenty-day production-company plan; full department staffing; stronger period build and crowd scope; separate stunt/medical-effects work; age-authentic minors possible; full broadcast/streaming delivery package. All amounts in USD; planning estimate, not a vendor bid.
Scenario | Production Company
Shoot days | 20
Performer / labor framework | SAG-AFTRA Television plus DGA/IATSE/Teamsters terms as applicable; lead and key creative fees include negotiated overscale placeholders
Framework ceiling / planning range | 6000000
Budget status | WITHIN STATED RANGE
Grand total | 4185385.8454
Account | Category | Line item | Cost type | Unit | Qty | Rate | Amount | Basis / note
1001 | Development & Above the Line | Life-story rights, releases and chain-of-title reserve | Service | allowance | 1 | 25000 | 25000 | Final rights strategy and participant releases require counsel
1002 | Development & Above the Line | Production rewrite / one-hour polish | Service | allowance | 1 | 30000 | 30000 | Lower tiers need location and speaking-role consolidation
1003 | Development & Above the Line | Producer fees | Crew payroll | flat | 1 | 110000 | 110000 | Financing fees and backend participations excluded
1004 | Development & Above the Line | Director | Crew payroll | flat | 1 | 110000 | 110000 | Full case is an overscale placeholder subject to DGA/signatory terms
1005 | Development & Above the Line | Casting director and sessions | Crew payroll | allowance | 1 | 25000 | 25000 | Includes day-player and young-looking performer search
1006 | Development & Above the Line | Production executive / network delivery supervision | Crew payroll | allowance | 1 | 30000 | 30000 | Company infrastructure allocation
Development & Above the Line subtotal | [6 empty] | 330000
2001 | Cast | Paid performers per Cast & Schedule | Cast payroll | linked total | 1 |  | 343650 | Gross wages; no deferrals or volunteer acting
Cast subtotal | [6 empty] | 343650
3001 | Production Management | Line producer / UPM | Crew payroll | day | 50 | 1300 | 65000 | Prep through wrap; micro combines functions
3002 | Production Management | Production coordinator | Crew payroll | day | 45 | 850 | 38250 | Paid office coordination
3003 | Production Management | 1st assistant director | Crew payroll | day | 28 | 1250 | 35000 | Prep, shoot and wrap coverage
3004 | Production Management | 2nd AD / background and minor coordination | Crew payroll | day | 20 | 1000 | 20000 | Added as crowds and minor work expand
3005 | Production Management | Script supervisor | Crew payroll | day | 20 | 900 | 18000 | Trauma, wardrobe and time-jump continuity
3006 | Production Management | Production assistants | Crew payroll | crew-day | 140 | 300 | 42000 | All PAs paid
3007 | Production Management | Office, printing, radios and communications | Purchase / rental | allowance | 1 | 18000 | 18000 | Production office and set communications
3008 | Production Management | Set medic / first aid | Crew payroll | day | 20 | 750 | 15000 | Present on principal days; dedicated stunt safety below
Production Management subtotal | [6 empty] | 251250
4001 | Camera | Director of photography | Crew payroll | day | 32 | 1900 | 60800 | Includes tests and limited prep
4002 | Camera | 1st assistant camera | Crew payroll | day | 20 | 1000 | 20000 | Camera focus and builds
4003 | Camera | 2nd AC / DIT / camera utility | Crew payroll | crew-day | 40 | 750 | 30000 | Combined roles below low tier
4004 | Camera | Camera, lenses and support package | Rental | shoot day | 20 | 4000 | 80000 | Full case includes two bodies and specialty lens support
4005 | Camera | Media, readers, checksum drives and backups | Purchase | allowance | 1 | 18000 | 18000 | At least two verified copies
4006 | Camera | Gimbal, jib, vehicle rig and specialty inserts | Rental | allowance | 1 | 20000 | 20000 | Bicycle, tunnel and wilderness moves
Camera subtotal | [6 empty] | 228800
5001 | Grip & Electric | Grip and electric crew | Crew payroll | crew-day | 120 | 850 | 102000 | Combined department in lower tiers
5002 | Grip & Electric | Lighting and grip package | Rental | shoot day | 20 | 2500 | 50000 | Hospital, night and period-location needs
5003 | Grip & Electric | Generator, distro, fuel and practical power | Rental / purchase | allowance | 1 | 15000 | 15000 | Remote park and wilderness coverage
Grip & Electric subtotal | [6 empty] | 167000
6001 | Production Sound | Mixer, boom and sound utility | Crew payroll | crew-day | 60 | 700 | 42000 | One-person micro; three-person full team
6002 | Production Sound | Recorder, wireless, timecode and boom package | Rental | shoot day | 20 | 1100 | 22000 | Hospital gowns and outdoor coverage require wireless planning
6003 | Production Sound | Playback, earwigs and specialty capture | Rental | allowance | 1 | 6000 | 6000 | Playback equipment only; music licenses separate
Production Sound subtotal | [6 empty] | 70000
7001 | Art Department & Props | Production designer / art director team | Crew payroll | crew-day | 90 | 1000 | 90000 | Design and prep scale with period depth
7002 | Art Department & Props | Set decoration, buyer and dress crew | Crew payroll | crew-day | 120 | 700 | 84000 | Paid construction/dress labor
7003 | Art Department & Props | Prop master and assistants | Crew payroll | crew-day | 22 | 1100 | 24200 | Hero prop continuity and stunt-safe duplicates
7004 | Art Department & Props | Paid screenplay props and hero art elements | Linked purchase / rental | linked total | 1 |  | 153900 | Detailed on Props & Art; included exactly once
7005 | Art Department & Props | General period set dressing and expendables | Purchase / rental | allowance | 1 | 35000 | 35000 | Hospital, school, retail, home and office layers
7006 | Art Department & Props | Period graphics, signage and trademark review | Service | allowance | 1 | 12000 | 12000 | Fictionalize brands where clearance is unavailable
7007 | Art Department & Props | Hospital / school redresses, flats and construction | Fabrication | allowance | 1 | 45000 | 45000 | Multiple scripted hospital and school environments
Art Department & Props subtotal | [6 empty] | 444100
8001 | Wardrobe, Hair & Makeup | Costume design, prep and set wardrobe | Crew payroll | crew-day | 70 | 850 | 59500 | 1975–78 continuity and multiples
8002 | Wardrobe, Hair & Makeup | Period wardrobe rentals, purchases and cleaning | Purchase / rental | allowance | 1 | 35000 | 35000 | Hero, day-player and background wardrobes
8003 | Wardrobe, Hair & Makeup | Hair and makeup crew | Crew payroll | crew-day | 80 | 850 | 68000 | Shaved-head continuity and trauma looks
8004 | Wardrobe, Hair & Makeup | Head wound, surgery and seizure prosthetics | Fabrication / consumable | allowance | 1 | 55000 | 55000 | Tests, appliances, blood and duplicates
8005 | Wardrobe, Hair & Makeup | Wigs, bald cap / shaved-hair effects and materials | Purchase / rental | allowance | 1 | 18000 | 18000 | Avoid repeated real shaving when continuity demands doubles
8006 | Wardrobe, Hair & Makeup | Intimacy coordinator / modesty garments / closed-set support | Crew payroll / purchase | allowance | 1 | 8000 | 8000 | For medical exposure and Sharon/stepfather material
Wardrobe, Hair & Makeup subtotal | [6 empty] | 243500
9001 | Locations | Location manager, scouts and assistants | Crew payroll | allowance | 1 | 30000 | 30000 | Scout and contract practical hospital/school alternatives
9002 | Locations | Location fees — hospital, school, retail, home and library | Location | allowance | 1 | 75000 | 75000 | No donated facilities assumed
9003 | Locations | Permits, parking, police, fire and public-safety support | Permit / service | allowance | 1 | 18000 | 18000 | Bike work, payphone/store, park and controlled fire
9004 | Locations | Cleanup, restoration, security and site protection | Service | allowance | 1 | 18000 | 18000 | Schools, hospitals and public interiors
9005 | Locations | Wilderness / river access and fire oversight | Location / service | allowance | 1 | 14000 | 14000 | Wildlife work remains contingent on approved plan
Locations subtotal | [6 empty] | 155000
10001 | Transportation & Travel | Transportation coordinator, captain and drivers | Crew payroll | allowance | 1 | 40000 | 40000 | Paid drivers and coordination
10002 | Transportation & Travel | Production vans, box truck and passenger vehicles | Rental | allowance | 1 | 38000 | 38000 | Scaled vehicle package
10003 | Transportation & Travel | Picture vehicles — Pontiac and period traffic | Rental | allowance | 1 | 35000 | 35000 | Hero vehicle prep is detailed in Props & Art; this covers operating rentals/traffic
10004 | Transportation & Travel | Fuel, mileage, tolls and parking | Purchase | allowance | 1 | 14000 | 14000 | Texas regional base
10005 | Transportation & Travel | Cast/crew lodging, airfare and per diem | Travel | allowance | 1 | 25000 | 25000 | Lower tiers rely on local hires; no unpaid lodging assumed
Transportation & Travel subtotal | [6 empty] | 152000
11001 | Stunts, Medical Effects & Safety | Stunt coordinator | Crew payroll | day | 10 | 1800 | 18000 | Current full coordinator reference retained even in reduced performer tiers
11002 | Stunts, Medical Effects & Safety | Bicycle rigs, mats, rehearsal space and safety equipment | Rental / fabrication | allowance | 1 | 32000 | 32000 | Protected jump, wheel failure and crash design
11003 | Stunts, Medical Effects & Safety | Knife choreography and stunt-safe weapon handling | Crew payroll / purchase | allowance | 1 | 6000 | 6000 | No sharp weapon used for contact work
11004 | Stunts, Medical Effects & Safety | Fire safety, rain / wet-weather and wilderness safety | Service | allowance | 1 | 6000 | 6000 | Campfire and exterior unit
11005 | Stunts, Medical Effects & Safety | Medical adviser and procedure review | Service | allowance | 1 | 12000 | 12000 | ER, surgery, seizure and recovery detail
11006 | Stunts, Medical Effects & Safety | Studio teacher / welfare worker / child labor coordinator | Crew payroll | allowance | 1 | 8000 | 8000 | Required scope depends on age-authentic minor casting and jurisdiction
Stunts, Medical Effects & Safety subtotal | [6 empty] | 82000
12001 | Visual Effects | VFX supervision, tests and turnover | Service | allowance | 1 | 12000 | 12000 | Plan crash and medical shots before photography
12002 | Visual Effects | Head injury, surgery and blood cleanup / enhancement | Service | allowance | 1 | 32000 | 32000 | Complements practical prosthetics
12003 | Visual Effects | Double vision, period cleanup and environment fixes | Service | allowance | 1 | 24000 | 24000 | POV work and removal of modern intrusions
12004 | Visual Effects | Wildlife / nature plates and comps | Service / license | allowance | 1 | 9000 | 9000 | Avoids unsupervised wildlife staging
Visual Effects subtotal | [6 empty] | 77000
13001 | Post-Production | Picture editor | Crew payroll | day | 100 | 1100 | 110000 | One-hour narrative editorial
13002 | Post-Production | Assistant editor / post coordinator | Crew payroll | day | 60 | 600 | 36000 | Combined with editor in micro case
13003 | Post-Production | Edit systems, storage, review and archive | Rental / purchase | allowance | 1 | 18000 | 18000 | Separate from camera originals
13004 | Post-Production | Sound editorial, Foley and design | Service | allowance | 1 | 55000 | 55000 | Brain-squish POV, hospital, bikes, wilderness and crowds
13005 | Post-Production | ADR, loop group and voice processing | Service | allowance | 1 | 10000 | 10000 | Gibberish/POV and public-space repairs
13006 | Post-Production | Final mix and M&E | Service | allowance | 1 | 25000 | 25000 | M&E for international delivery
13007 | Post-Production | Color grade and finishing | Service | allowance | 1 | 25000 | 25000 | Period look and medical continuity
13008 | Post-Production | Online, conform and mastering | Service | allowance | 1 | 28000 | 28000 | Broadcast/streaming masters
13009 | Post-Production | QC, captions, audio description and deliverables | Service | allowance | 1 | 10000 | 10000 | Accessibility and distributor deliverables
13010 | Post-Production | Archival / stock footage and wildlife licenses | License | allowance | 1 | 12000 | 12000 | Quote required; no unlicensed use
Post-Production subtotal | [6 empty] | 329000
14001 | Music | Music supervisor / clearance administration | Service | allowance | 1 | 9000 | 9000 | Begin before scripted playback
14002 | Music | Composer fee | Service | allowance | 1 | 30000 | 30000 | Original score
14003 | Music | Score recording, musicians, studio and mix | Service | allowance | 1 | 10000 | 10000 | Mostly in-the-box below full tier
14004 | Music | Source-song master and publishing licenses | License | allowance | 1 | 170000 | 170000 | Premium catalog cues require separate master and publishing quotes; zero means replacement
14005 | Music | Cue sheets, music legal and license delivery | Service | allowance | 1 | 5000 | 5000 | Required delivery paperwork
Music subtotal | [6 empty] | 224000
15001 | Insurance, Legal, Admin & Delivery | Production package insurance | Insurance | allowance | 1 | 60000 | 60000 | GL, equipment, auto and specialty-risk allowances
15002 | Insurance, Legal, Admin & Delivery | Production legal, contracts and clearances | Service | allowance | 1 | 28000 | 28000 | Rights, brands, sensitive material and releases
15003 | Insurance, Legal, Admin & Delivery | Production accounting and cost reporting | Service | allowance | 1 | 18000 | 18000 | Cost reports and tax filings
15004 | Insurance, Legal, Admin & Delivery | Errors & omissions insurance | Insurance | allowance | 1 | 22000 | 22000 | Common distributor requirement
15005 | Insurance, Legal, Admin & Delivery | Publicity stills, EPK and delivery incidentals | Service | allowance | 1 | 18000 | 18000 | Distribution marketing spend excluded
15006 | Insurance, Legal, Admin & Delivery | Production-company overhead | Overhead | allowance | 1 | 100000 | 100000 | Corporate infrastructure allocation; financing costs excluded
Insurance, Legal, Admin & Delivery subtotal | [6 empty] | 246000
Subtotal before payroll burdens and contingency | [6 empty] | 3343300
Cast pension & health | [6 empty] | 73884.75
Crew payroll taxes / workers compensation / benefits burden | [6 empty] | 306072.5
Payroll company fee | [6 empty] | 58604
Subtotal before completion bond and contingency | [6 empty] | 3781861.25
Completion bond | [6 empty] | 75637.225
Contingency reserve | [6 empty] | 327887.3704
GRAND TOTAL | [6 empty] | 4185385.8454

## Sources & Checks
Sources, Controls & Audit Checks
Rates and thresholds are planning references. Final agreement, overtime, zone, residual, benefit-ceiling and minor rules must be confirmed with the applicable guilds and payroll company before hiring.
Item | Value / rate | Units | As of | Source | URL / reference | Use in model
Attached screenplay | 11,266 words / 54 slug lines | text | 2026-08-15 | User-provided screenplay | Pasted text(20260816-021427).txt | Primary basis for cast, props, locations, action and schedule
SAG-AFTRA Micro-Budget Project Agreement | $20,000 maximum per episode | total budget | 2026-08-15 | SAG-AFTRA | https://www.sagaftra.org/production-center/contract/884/getting-started | Not viable for this full script; Micro is a colloquial label in this workbook
Special New Media budget tiers | A: $50k–<$300k; B: $300k–<$700k; C: $700k–<$1m; D: $1m+ | per episode | 2026-08-15 | SAG-AFTRA | https://www.sagaftra.org/sites/default/files/2023%20Special%20Agreement%20for%20Independent%20Producers%20of%20Dramatic%20New%20Media%20Programs%20Rate%20Sheet.pdf | Eligibility depends on episodic/new-media status and current agreement
Category A performer / background | $257 / $173 | per day | 2026-07-01 | SAG-AFTRA 2026 Category A rate sheet | https://www.sagaftra.org/sites/default/files/2026-07/CURRENT%20Special%20New%20Media%20Rate%20Sheet%20-%20Category%20A.pdf | Reference floors for Micro; lead is budgeted overscale
Category B performer / weekly / background | $449 / $1,560 / $231 | minimum | 2026-07-01 | SAG-AFTRA 2026 Category B rate sheet | https://www.sagaftra.org/sites/default/files/2026-07/CURRENT%20Special%20New%20Media%20Rate%20Sheet%20-%20Category%20B_0.pdf | Reference floors for Ultra-Low
Category C performer / weekly / background | $834 / $2,896 / $231 | minimum | 2026-07-01 | SAG-AFTRA 2026 Category C rate sheet | https://www.sagaftra.org/sites/default/files/2026-07/CURRENT%20Special%20New%20Media%20Rate%20Sheet%20-%20Category%20C.pdf | Shown for comparison; Low tier instead assumes full television rates
Full television day / weekly reference | $1,283 / $4,455 | minimum | 2026-07-01 | Implied by current 20% / 35% / 65% Special New Media sheets | https://www.sagaftra.org/production-center/contract/810/rate-sheet/document | Reference floors for Low and Production Company
One-hour major role formula | 130% × day performer scale × 8 days | episode minimum | 2026-08-15 | SAG-AFTRA 2026 TV/Theatrical contract explainer | https://www.sagaftra.org/contracts-industry-resources/contracts/2026-tvtheatrical-contracts | Production-company lead placeholder exceeds this minimum
Cast P&H planning rate | 21.5% | % gross | 2026-09-06 | SAG-AFTRA 2026 Special New Media rate sheets | https://www.sagaftra.org/sites/default/files/2026-07/CURRENT%20Special%20New%20Media%20Rate%20Sheet%20-%20Category%20B_0.pdf | Applied to total gross cast payroll; confirm ceilings and allocation
DGA rate cards | Current 2026–27 schedules | reference | 2026-07-22 | Directors Guild of America | https://www.dga.org/Contracts/Rates-2026-to-2027 | Production-company creative/AD assumptions require final DGA review
Music clearances | Written quote required | master + publishing | 2026-08-15 | Production assumption | N/A | The Archies, Pink Floyd and Led Zeppelin are not cleared by this estimate
Tax incentives | Not netted | treatment | 2026-08-15 | Conservative budgeting policy | N/A | All options show gross cost before rebates, grants or credits
Check | Actual | Expected / limit | Difference | Tolerance | Status | Where to fix / note
Micro total below Category A ceiling | 223160.633 | 300000 | -76839.367 | 0 | OK | Micro Budget / Assumptions
Ultra-Low total below Category B ceiling | 600218.8237 | 700000 | -99781.1763 | 0 | OK | Ultra-Low Budget / Assumptions
All four paid prop totals are positive | 245200 | 0 | 245200 | 0 | OK | Props & Art
Micro Budget category subtotal tie-out | 196101 | 196101 | 0 | 1 | OK | Micro Budget category subtotals
Ultra-Low Budget category subtotal tie-out | 518365 | 518365 | 0 | 1 | OK | Ultra-Low Budget category subtotals
Low Budget category subtotal tie-out | 1211381.5 | 1211381.5 | 0 | 1 | OK | Low Budget category subtotals
Production Company category subtotal tie-out | 3343300 | 3343300 | 0 | 1 | OK | Production Co category subtotals
Summary totals tie to detailed budgets | 6459493.0008 | 6459493.0008 | 0 | 1 | OK | Summary / detailed budgets
No incentive proceeds reduce displayed budgets | 0 | 0 | 0 | 0 | OK | Assumptions; incentives excluded
MODEL STATUS |  |  |  |  | PASS